## Slide 1: January 2015
APAC iSoftStone Transition Overview
Notes: Master Content Slide

## Slide 2: Agenda
What is Managed Services
Transition Objectives and Expectations
Transition structure, team members and roles
Communications Planning
Transition Schedule
  Knowledge Transfer
  Secondary Support
  Primary Support
Acceptance Criteria
  KT Sessions
  Satisfactory Transition Completion
Meetings, Cadence and Schedule
GSC Update
Risk Management

## Slide 3: Transition Objective
Guide a smooth turnover of IT support for APAC applications to support Avon. This will be accomplished by:
  Meeting Transition timeline
  Achieving minimal disruption to the business while providing consistent support at required levels.

## Slide 4: What is Managed Services

## Slide 5: Sourcing models have evolved with increasing sourcing maturity demanded by clients
High
Low
High
Low
Economic Impact 
Increasing Sourcing Maturity
Cultural Impact 
Staff Augmentation
Out-tasking
Managed Services
Project based Outsourcing

## Slide 6: Attributes of a Managed Services Model
Staff augmentation services are contracted to obtain supplemental resources needed by the organization on a contingent-assignment basis to perform its responsibilities. Client continues to own the risk of time, budget, and scope of delivery, and managing the output of the resources provided. These resources augment the existing staff.
Managed services are contracted to obtain the desired outcome from a scope of work. The risk of time, budget, and delivery is transferred to the vendor and performance is governed by SLAs and metrics. The client does not need to know who is doing the work or where they are located, with the exception of resources designated as “key” or if there is a specific requirement to be on site.
A Master Services contract between the service provider and the client governs the relationship, including how work is defined (work orders), how costs are calculated and how work is approved (outcome based managed services)

## Slide 7: Alignment of Scope and Pricing
Break Fix
Error Correction
Patch Management
Required Modifications (legal and regulatory)
Application Tuning
Application Optimization
Master Data Maintenance
Enhancements (equal to or less than 160/320 productive hours)
Elective
New releases
Minor upgrades
Activation of SW & Enhancement Packs
Testing
Large Enhancements (greater than 160 productive hours)
Projects
Discretionary
Potential to bundle multiple Enhancements
Potential to break up larger enhancements into smaller enhancements.
Major Upgrades
New capabilities / applications
Testing
Application Maintenance & Support
Application Development
Cross Functional & Governance
Tools & Enablement Technology
Fixed Fee
Defined Capacity
Defined Capacity

## Slide 8: Attributes of a Managed Services Model
  Using Metrics and SLAs
    Development Metrics
      Timeliness
      Cost
      Scope
      Quality and Customer Satisfaction
    Support Metrics
      Incident Response Time
      Incident Resolution Time
      Application Availability
      Quality and Customer Satisfaction

## Slide 9: Service Level Management
Support Metric Grouping | Service Level Description | Service Level Class | Minimum Service Level | Expected Service Level
Incident Management | Incident Resolution Timeliness - Priority 1 | CPI | 90% | 95%
 | Incident Resolution Timeliness - Priority 2 | CPI | 90% | 95%
 | Incident Resolution Timeliness - Priority 3 | KPI | 90% | 95%
 | Incident Resolution Timeliness - Priority 4 | GPI | 90% | 95%
 | Incident Response Timeliness - Tier 1 Applications | KPI | 90% | 95%
 | Incident Response Timeliness - Tier 2 Applications | KPI | 90% | 95%
 | Incident Response Timeliness - Tier 3 Applications | KPI | 90% | 95%
 | Incident Resolution Quality | KPI | 90% | 95%
Problem Management | % Root Cause Analyses completed (Priority 1 & 2 Incidents) | CPI | 90% | 95%
App Availability | Application Availability Tier 1 | CPI | 99.25% | 99.75%
 | Application Availability Tier 2 & Tier 3 | KPI | 98% | 99%

## Slide 10: Elements of a Work Order
1. Outcome - Milestone or Deliverable
2. Requirements
In-scope – deliverable / milestone
Out-of-scope
Assumptions
Dependencies
3. Time
Start date
End date
4. Acceptance Criteria
Notes: A WO is framed by the milestone or the deliverable and includes requirements, time, and acceptance criteria. A document is uploaded to Clarity in standard Avon format which has all this information in it – enough information for Service Provider to estimate the work. We will be working on a template for the work order description including acceptance criteria.

## Slide 11: How Do We Get There

## Slide 12: Transition Structure & Roles
APAC
iSoftStone
Leadership /
Steering
Committee
Transition
Management
Office
Karen Salgado
Christine Addonizio
Gary Venner
Cliff Cuseo
TBD APAC
Anna Xu
Sam Hu
Transition
Teams
Transition Teams
Johnsen Zhang
William Feng
YuTing Tan
Richard Hutchings ANZ
Hermann Yang Taiwan
Stephen Zhang China
Location
Guangzhou
Remote
Remote

## Slide 13: Transition Teams
China
Taiwan
ANZ
iSoftstone Track Leads |  |  |  | Avon |  |  | 
Application | Contact | Contact Number | Email |  | Contact Name | Contact Number | Email
Interfaces/reporting/emails/archiving | Johnsen Zhang | +86-13724155258 | shengzhangh@isoftstone.com | Manager | Tiffany Chung | +886-2-29016060 ext. 2951 | Tiffany.Chung@avon.com
DRMPOS | Paul Zhang | +86-15914538629 | ljzhanga@isoftstone.com | SME Functional | Henry Hung | +886-2-29016060 ext. 2957 | Henry.Hung@avon.com
DRMARMS | Paul Zhang | +86-15914538629 | ljzhanga@isoftstone.com | SME Functional | Jenny Yang | +886-2-29016060 ext. 2950 | Jenny.MJ.Yang@avon.com
DMS | Jim Wu | +86-15521370169 | jmwuc@isoftstone.com | SME Technical | Hannah Lee | +886-2-29016060 ext. 2958 | Hannah.Lee@avon.com
CIA | Selin Ou | +86-13450189197 | slou@isoftstone.com |  |  |  | 
Interfaces/reporting/emails/archiving | Johnsen Zhang | +86-13724155258 | shengzhangh@isoftstone.com | Manager | Richard Chen | +86-20-22368868 | Richard.Chen@avon.com
DRMSP | Fred Li | +86-13266883910 | zqlim@isoftstone.com | SME Functional | Bill Chen | +86-20-22368859 | Bill.Chen@avon.com (*CTI)
ADCP | Fred Li | +86-13266883910 | zqlim@isoftstone.com | SME Functional | Gerry Yang | +86-20-22368827 | Gerry.Yang@avon.com
CIA | Yu Lei | +86-15817418348 | leiyua@isoftstone.com | SME Technical |  |  | 
KPI | Yu Lei | +86-15817418348 | leiyua@isoftstone.com |  |  |  | 
RB3 - Representative Billing | William Feng | +86-18689413237 | zyfengd@isoftstone.com | Manager (AS400) | Ulrich Jensen | +61-2-9936-7333 | Ulrich Jensen@avon.com
MACPAC | William Feng | +86-18689413237 | zyfengd@isoftstone.com | Manager (dotNet) | Josh Titley | +61-2-9936-7335 | Josh.Titley@avon.com
OLA | Will Liang | +86-13660161448 | jhliange@isoftstone.com | SME Functional | George Zhao | +61-2-9936-7480 | George.Zhao@avon.com
SICS | Will Liang | +86-13660161448 | jhliange@isoftstone.com | SME Technical | David Hoschke | +61-2-9936-7657 | David.Hoschke@avon.com
AWARES | William Feng | +86-18689413237 | jhliange@isoftstone.com |  |  |  | 
Interfaces/reporting/emails/archiving | William Feng | +86-18689413237 | zyfengd@isoftstone.com |  |  |  | 

## Slide 14: Communications Plan
Audiences and responsible team members
  All APAC Avon IT personnel
  Transition Team Members – Avon and iSoftStone
  Avon personnel who will be retained
  iSS support team
  Business users
  Accounting
  GSC
Communication documents available
  Transition Planning deck
  Introduction to Managed Services
  Service Level Methodology
  Work Order Management (when necessary)

## Slide 15: Transition Timeline (Project Plan with task owner)

## Slide 16: Transition Timeline (Project Plan Functional)
Tasks/ Timelines | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
(week of) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Verify application inventory and priority |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Define and update application check list for any differences |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Define System Functions and Modules List |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Create transition checklist |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Transfer the information of application environments(Dev/QA/Prod) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Transfer production support processes of different markets |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Transfer Application Release / Deployment Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Transfer requirements by modules |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Transfer system design/ configuration and customized codes |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Verify transition checklist |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Knowledge and core functions review by ISS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pilot run on testing system |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Shadow coach on daily working with Avon IT team |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Taking over the responsibilities of Avon IT team |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Production support |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Knowledge Transfer |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GSC Updates |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Remedy Updates |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Communication Facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 17: Transition Timeline – Australia/New Zealand
Application/ Timelines (week of) | 12-Jan | 19-Jan | 26-Jan | 2-Feb | 9-Feb | 16-Feb | 23-Feb | 2-Mar | 9-Mar | 16-Mar | 23-Mar | 30-Mar | 6-Apr | 13-Apr | 20-Apr | 27-Apr | 4-May
Communication plan – IT associates | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Kick Off and transition planning | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RB3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MACPAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
OLA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SICS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
AWARES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Interfaces/reporting/emails/archiving |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Knowledge Transfer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Shadow Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Primary Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Steady State |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 18: Transition Timeline - China
Application/ Timelines (week of) | Jan 12 | Jan 19 | Jan 26 | Feb 2 | Feb 9 | Feb 16 | Feb 23 | Mar 2 | Mar 9 | Mar 16 | Mar 23 | Mar 30 | Apr 6 | Apr 13 | Apr 20 | Apr 27
Communication plan – IT associates | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Kick Off and transition planning | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  | 
DRMSP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
AXAPTA - WMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CIA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ADCP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
KPI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Interfaces/reporting/emails/archiving |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Knowledge Transfer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Shadow Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Primary Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Steady State |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chinese New Year Holiday

## Slide 19: Transition Timeline - Taiwan
Application/ Timelines (week of) | Jan 12 | Jan 19 | Jan 26 | Feb 2 | Feb 9 | Feb 16 | Feb 23 | Mar 2 | Mar 9 | Mar 16 | Mar 23 | Mar 30 | Apr 6 | Apr 13 | Apr 20 | Apr 27
Communication plan – IT associates | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Kick Off and transition planning | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  | 
DRMPOS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DRMARMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
AXAPTA - WMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CIA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Interfaces/reporting/emails/archiving |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Knowledge Transfer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Shadow Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Primary Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Steady State |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chinese New Year Holiday

## Slide 20: Knowledge Transfer

## Slide 21: Transition Planning Phase
Determine Required KT Sessions
Identify knowledge Providers (Avon) and Consumers (iSS) of knowledge in KT Phase
Get Sign-off of planned sessions from Avon and iSS
Location – time frame to be on site in Guangzhou
Schedule sessions
  Knowledge Provider should spend time assembling documentation/data
    Relevant technical documentation
    Overview (Business/Technology and Historical Info)
Determine system access requirements
Recommend use of Web Conference to record for later viewing
TP
PS
SS
KT

## Slide 22: Application Data Requirements Preparation for KT
Track | Documentation |  | Application Profile | Level of Customization |  |  | Operating Profile |  | Incident History | Other Comments
 | Document Name | Location Stored | What ar the major processing steps or modules | If used out of the box, what is the current release | If customized what was the functionality added? | If customized which modules were added or changed, and to what extent | Production abnormalities | Events to be aware of that happen often or periodically | Illustrate production issues | What else should iSoftstone need to be aware of
RB3 - Representative Billing (ANZ) |  |  |  |  |  |  |  |  |  | 
ANZ - MACPAC (ANZ) |  |  |  |  |  |  |  |  |  | 
OLA – (ANZ) |  |  |  |  |  |  |  |  |  | 
SICS (ANZ) |  |  |  |  |  |  |  |  |  | 
AWARES(ANZ) |  |  |  |  |  |  |  |  |  | 
Interfaces/reporting/emails/archiving |  |  |  |  |  |  |  |  |  | 
DRMPOS (Taiwan) |  |  |  |  |  |  |  |  |  | 
DRMARMS (Taiwan) |  |  |  |  |  |  |  |  |  | 
DMS (Taiwan) |  |  |  |  |  |  |  |  |  | 
CIA (Taiwan) |  |  |  |  |  |  |  |  |  | 
AXAPTA(Taiwan) |  |  |  |  |  |  |  |  |  | 
DRMSP (China) |  |  |  |  |  |  |  |  |  | 
ADCP (China) |  |  |  |  |  |  |  |  |  | 
CIA (China) |  |  |  |  |  |  |  |  |  | 
KPI (China) |  |  |  |  |  |  |  |  |  | 
AXAPTA (China) |  |  |  |  |  |  |  |  |  | 

## Slide 23: Transition process
 | Transition Planning | Knowledge Transfer | Secondary Support | Primary Support
AVON Responsibility | • Re-verification of the list of all applications to be included in the cluster • Identification of appropriate SME’s for KT/SS/PS and confirm availability • Prioritization of applications within the cluster by criticality and size • Discuss by application: • The key components and important support activities • Level of customization • Governance: Introduction to Managed Services | • Availability for KT sessions • Application Overview • Business • Technical • Functional • Application walkthrough • Discussion on application interfaces • Database details • Code walk through of critical components • Support Overview • Support Activities • Typical tickets • Open tickets • Application Environments & Installation • Weekly Q&A • Attend reverse presentations • Reverse KT evaluation • Application Information Document Review | • Review of code changes / fixes, impact analysis done by ISS • Clarification of additional questions and issues for ISS • Joint walkthrough of complex code changes and bug-fixes done by Avon • Governance: Service Level Agreements • GSC/Remedy updates • System Access | • Review of complex or critical code changes / fixes, impact analysis done by vendor • Assist vendor team in resolving incidents and requests, if required by vendor • Governance: Meetings and Reporting
ISS Responsibility | • ISS internal training for AVON business • Classify the applications by Application Programming Language • Assign proper staffs to take up different applications • Identification of necessary information for KT | • Assignation of appropriate staff to participate KT sessions • Collection of Documents • refer to System level check list • Summarize necessary supporting knowledge (ISS localization refer to check list) • KT evaluation • Preparation of reverse presentation | • Resolving incidents and requests with AVON team • Raise additional questions and issues to SME if any • Collect information of code changes and bug-fixes • Provide details of code changes/fixes, impact analysis to AVON team | • Resolve incidents and requests • Acquire advices from SME for criticall incidents and mark down appropriate solution
Output | • Develop and generate document of basic concept for AVON business • Transition Flow • Applications - Staffs mapping • Transition team contact list • KT check list | • Completed KT check list • Build up system information data base • Generate support guide for different systems (Cover: 1.functional knowledge 2.operational knowledge 3.Application technical environment 4.Incident handling procedure) •Accomplished reverse presentations | • Fulfil Service Level Agreements • Improve the quality of system information database on ISS site • Improve the quality of support guide on ISS site | • Fulfil Service Level Agreements • Improve the quality of system information database on ISS site • Improve the quality of support guide on ISS site

## Slide 24: Transition Objectives by Phase
Transition Planning
Knowledge Transfer
Secondary Support
Primary Support
Key objectives:
Create detailed transition plan
Setup initial technical infrastructure
Create SME schedule
Develop detailed work stream plans
Key objectives:
Acquire domain / technical / process knowledge from SME
Reverse KT - present the knowledge back
Prepare Application Information Document (AID)
Key objectives:
Resolve historical / live tickets with SME’s help
Gain hands on experience on support process flow
Update AID
Key objectives:
Resolve live tickets independently
Kick off SLA baseline methodology
Establish plan for communication in Steady State

## Slide 25: Expectations during Transition
Transition Planning | Knowledge Transfer | Secondary Support | Primary Support
Re-verification of the list of all applications to be included in the cluster Identification of appropriate SME’s for KT/SS/PS and confirm availability Prioritization of applications within the cluster by criticality and size Discuss by application: The key components and important support activities Level of customization Governance: Introduction to Managed Services | Availability for KT sessions Application Overview Business Technical Functional Application walkthrough Discussion on application interfaces Database details Code walk through of critical components Support Overview Support Activities Typical tickets Open tickets Application Environments & Installation Weekly Q&A Attend reverse presentations Application Information Document Review | Review of code changes / fixes, impact analysis done by ISoftStone Clarification of additional questions and issues for ISoftStone Joint walkthrough of complex code changes and bug-fixes done by Avon Governance: Service Level Agreements GSC/Remedy updates System Access | Review of complex or critical code changes / fixes, impact analysis done by vendor Assist vendor team in resolving incidents and requests, if required by vendor Governance: Meetings and Reporting
During the transition, Avon is still responsible for application changes and incident support

## Slide 26: KT Status Reporting
 |  |  | THIS PERIOD |  |  |  |  |  |  | CUMULATIVE |  |  | 
 |  |  | Forecast | Actual KT Sessions |  |  | Reverse KT |  |  | Actual Through Current Period |  |  | 
Category | Planned Completion % | Actual Completion % |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Completed | Rescheduled | Rating | Completed | Rescheduled | Rating | Total Meetings | Completed KT | Completed RKT | Average rating
TP
PS
SS
KT

## Slide 27: Post Session(s)
KT Evaluation
  KT consumer (iSS) has 2 business days to fill out the rating template
  iSS will rate the session 1-5
  Minimum rating of 3 required to validate the quality of the session
    If less than 3, remediation session will be scheduled within one - two business days
Reverse KT
  Reverse KT will be provided by the iSS consumer back to Avon reflecting their understanding of the session
  Avon will rate this session 1- 5
  Minimum rating of 3 required to validate the quality of the session
    If less than 3, remediation session will be scheduled within two business days
TP
PS
SS
KT

## Slide 28: KT Acceptance Template
Knowledge Transfer Acceptance |  | 
INSTRUCTIONS (input fields are in yellow) |  | 
In rating each of the detailed criteria, ensure that you take into account: |  | 
- Application complexity (number of processes, functionality, interfacing, etc.) |  | 
- Application criticality (business critical application/customer facing, etc.) |  | 
Rating Criteria - if any criteria is rated at <3, clear reasons for this must be stated in the Comments column. |  | 
1: Poor |  | 
2: Below Expectations |  | 
3: Met Expectations |  | 
4: Exceed Expectations |  | 
5: Excellent |  | 
TEAM |  | 
Team Member completing evaluation form |  | 
Date |  | 
Tower Name |  | 
Application Name |  | 
Name of Session |  | 
Start time & End time of session |  | 
How much time did you spend preparing for this session? |  | 
KT FEEDBACK | Rating | Comments
Adequate time was allowed for conducting the KT sessions |  | 
Was the agenda for the sessions covered adequately |  | 
Coverage of Functional Knowledge |  | 
Coverage of system demo's |  | 
Coverage of all interfaces and 3rd party interactions related to the application |  | 
All necessary documentation has been provided and explained |  | 
Coverage of Technical knowledge relating to the application |  | 
Coverage of Business process / Business Events knowledge relating to the application |  | 
Coverage of History of known problems and issues relating to the application |  | 
Coverage of DB relating to the application |  | 
Coverage of code walkthrough of the application |  | 

## Slide 29: KT Rating Questions
Adequate time was allowed for conducting the KT sessions.
Functional knowledge relating to the application is explained and understood.
Operational knowledge relating to the application is explained and understood.
All non-core activities have been explained and understood.
The Application technical environment (e.g. Integrations, Infrastructure, Dependencies) has been explained and understood.
Technical knowledge relating to the application is explained and understood.
Business process / Business event knowledge relating to the application is explained and understood.
TP
PS
SS
KT
Notes: Rating of 1-5, 5 being best.

## Slide 30: Acceptance Criteria for Secondary/Primary Support
Acceptance Criteria Secondary Support
Number/percentage of tickets addressed successfully (TBD) by priority
Number/percentage of tickets addressed successfully within SLA (TBD)
Concerns from KT
TP
PS
SS
KT
Number of tickets resolved independently by priority (TBD)
Number/percentage of tickets resolved independently within SLA (TBD)
Concerns from Secondary Support
Acceptance Criteria Primary Support

## Slide 31: Transition Completion Acceptance Criteria
KT sessions all satisfactory
Secondary Support satisfactory
Primary Support satisfactory
GSC, Accounting and Business Users updated on changes
Milestone completion
Other TBD

## Slide 32: Risk Management
Risk ID | Short Description | Impact | Responsible Individual | Action to be taken
001 | Remote transition team may lead to less effective KT | Knowledge transferred will be insufficient to pass SS and PS | Track Coordinator | Rate meeting success accurately, completely and immediately
002 | Avon team members may leave early | Knowledge leaves with them | Track Coordinator | Update documentation; accelerate AID process; record KT sessions
003 | Third party application support | Requires Avon sign-off | Track Coordinator | Avon team lead must be part of KT sessions with 3rd party vendor

## Slide 33: Transition Status and Management Meetings
Transition team status review - weekly
  iSS to prepare deck and report
  Transition team leads – Avon, iSS and VSMO
Transition management teams – as necessary
  Avon management, iSS management, VSMO
Steering Committee - TBD
  Ad hoc
  Final Acceptance
GSC - TBD
  Contact names
  Escalation Procedures
  Remedy Groups

## Slide 34: Immediate Next Steps
Identify, Communicate to and Organize Transition Teams – iSS and Avon
Complete transition planning
  Identify all resources by application
  Finalize agendas for KT sessions
  Identify Travel Requirements to Guangzhou and Ireland
Kick Off Meeting
Introduction to Managed Services
Schedule and Begin KT Sessions

## Slide 35: Thank You
Notes: Master Closing Slide