## Slide 1: Asia IT Transformation Town Hall w/ IT Leads

## Slide 2: Agenda
Words from our incoming CIO – Sue Liddie
Current IT environment – Challenges and Opportunities
IT Transformation Commitment
Transition Methodology
Steady State Governance
Case Study: SMT
Role of IT Lead
Next Steps
Appendix
iSoftStone Annual Review Highlights

## Slide 3: Current IT environment – Challenges and Opportunities
Background:
APAC IT has been locally focused. Local IT teams build own solution and structure supporting local priorities
IT landscape is diversified and localized. Systems and processes are different by markets, no synergies.
Aggressive local IT reduction since 2008 with significantly increase in IT demands due to reduction effort
Regional team created up in 2012 to provide centralize and share IT support / know-how on common IT systems / processes with good outcome: $180K/year savings on centralized IT operations; $1M cost avoidance on consolidating Axapta upgrade program for 4 markets
Challenges / proposal:
Internal –
Continue to simplify IT landscape and consolidate common IT systems, processes & infrastructure. Maximize synergies with share services to drive down C&B and running costs (servers, licenses, IT resources)
Manage global / regional projects centrally to gain efficiency & reduce overhead on local IT
Address 3 major areas taking up lots of local IT resources: ad-hoc data / reporting requests, local campaign structure set up, and branch IT support. Find measures to address them (self services on reports, simplify campaign set up process, outsource field support for cost reduction)
Business –
Upgrade platform to become real-time oriented and ready for e-commerce/multi-channel
Support local sales leadership model set up, strengthen field management capability
Early discussions on business direction for assessing and readying IT capability

## Slide 4: IT Transformation Commitment
Maintain current business commitments with no disruptions
Retain Avon Specific Knowledge
Build comprehensive Application Information Documentation (AID) via the transition
Improve and standardize Service Levels across the region
Conclude transition schedule based on satisfactorily completing each stage gate based on agreed upon: 1) acceptance criteria; 2) targets; and, 3) sign-offs
Institutionalize governance of outsourcing partner
  On demand issue resolution and risk mitigation
  Daily Incident, Service Request, and work order review
  Weekly SLA reporting
  Monthly demand planning and Steering Committee

## Slide 5: Transition Principles
Application and Function Clustering
  Transition Clusters will be formed for each markets by logically grouping applications and/or functions sharing:
    Similar business processes and interfaces
    Similar technology stack
    Supported by the same SMEs
    Sharing a common support model (Where L2/L3 is done internally vs requiring co-ordination with package vendors)
    Application with similar level of complexities
Timeline
  Complex and critical applications have a longer transition as represented in the transition timeline
  Simple and Medium applications will have relatively lesser duration of transition
  Transition of clusters will happen in parallel as they will be independent of each other
  However all transitions are right aligned to steady state operations in order to ensure consistent level of services across all the transition clusters

## Slide 6: Transition Methodology – Following A Proven Process
Objective: Achieve a rapid understanding of the business processes, comprehensive knowledge transfer and swift takeover of in-scope services, while minimizing business interruption, enabling agreed levels of support, and enhancing the capability for continuous improvement.
Transition Planning
Transition
Steady State
Create detailed Transition Plan
Setup initial access to offshore
Sign off Contract
Kick Off transition work streams
Create SME Schedule
Acquire domain / technical / process knowledge from SME
Reverse presentation of the knowledge back
Prepare System Appreciation Document (SAD)
Resolve historical / live tickets & enhancements with SMEs help
Gain hands on experience on support process flow
Update SAD
Resolve live tickets independently
Deliver enhancements independently
Establish plan for communication in Steady State
Knowledge Transfer
Secondary Support
Primary Support
Ongoing improvements, Rationalizations, Productivity, Transformation
Interview/ Workshop calendar for the Transition published
Infrastructure setup kickoff
Completion of Knowledge Acquisition
Stage Gate Review for KT completion
Transition of Primary Responsibility to iSoftStone
Stage Gate Review for SS completion
iSoftStone assumes complete support for all applications
Stage Gate Review for Primary Support
100% SLA ownership

## Slide 7: Transition Methodology – Guiding Principles
100 % coverage of Transition areas by detailed Due Diligence of applications and infra services
  Identify critical and key areas of transition that will be agreed by iSoftStone and Avon (SMEs & Business) that is key for success of transition
Optimized utilization of SME time through KT without interrupting Business service levels by
  Onboarding the team that would have undergone Avon Business and process KT thus using SME time only for the application specific KT
  Preparedness of the team before attending the KT sessions by going through the existing documentation, walk through of applications and code analysis
  Prioritizing the KT sessions based by clustering the applications and leveraging SME time according to the criticality of the applications
  Recording of the sessions to review for any clarifications before reaching out to the SMEs
Seamless transition with no service level impact through a structured process that involves
  Periodic touch points with the business over the duration of the transition to show progress and build confidence through KPI status
  Leverage primary support phase to directly work with business team and understand their expectations before moving into steady state operations
  Periodic review of incident / enhancements status and prioritizing as per business needs
Dedicated Transition Management Office that will over see the entire transition and would involve stakeholders from iSoftStone, AVON (IT & Business)
Effective Risk Management and Governance to capture risks early enough and mitigate through the appropriate governance processes

## Slide 8: Transition Risk and Mitigation Strategy
# | Risk | Probability | Impact | Mitigation options
1 | Non availability of Incumbent team members and SMEs | Probable | High | Set expectations of time required from Avon and incumbent vendors’ teams upfront and agree upon this during Transition Planning (Avon and iSoftStone)
2 | Attrition (especially of the key staff) prior to completion of transition | Highly likely | High | Identify staff that are very likely to leave and arrange backup staff and have a prioritized knowledge transfer (Avon) Identify `high risk’ transition items and prioritize their transition (iSoftStone) VISA planning for flight risk
3 | Lack of cooperation, resistance to change or hostility from staff/vendors, during the transition process | Probable | High | Identify and form a set of `incumbent champions’ who would play a mediating role during the transition. (Avon) Involve all the key stakeholders in the transition plan and obtain sign-off (Avon and iSoftStone)
4 | Surge of support incidents takes away time from transition | Probable | High | Prioritize support incidents and push out resolution of low impact items (Avon and iSoftStone). Assist the incumbent team in resolving the incidents (iSoftStone)
5 | Gaps in Knowledge Transfer | Probable | High | Clearly state before hand to Avon, the resource requirements at different stages of transition process (iSoftStone)
6 | Lack of communication of transition program to Avon's employees and incumbent team | Probable | High | Work with Avon to set up a general kick-off meeting which gives an opportunity to the iSoftStone client manger and Service Delivery Manger to address the key personnel
7 | Delay in providing system access to iSoftStone personnel against transition plan | Probable | High | Avon to ensure that the necessary access permissions will be provided to identified iSoftStone personnel during Transition Planning phase Avon to establish on-boarding procedure to take care of this Proactively inform Avon on access requirements of resources as per on-boarding process (iSoftStone)

## Slide 9: Transition Framework
Up to 3 weeks
Ongoing
Service Levels
Application Sequencing
Infrastructure
Organizational Change Management
Inventory & Assessment
Infrastructure & Process Setup
(Team, Infrastructure, Processes, etc.)
Organization Change Management
Knowledge Transfer (KT)
Secondary Support (SS)
Primary Support (PS)
Ongoing Improvements - Rationalization, Productivity
Interview/ Workshop calendar for the transition published
Infrastructure Setup Kickoff
Completion of Knowledge Acquisition
Transition of Primary Responsibility to iSoftStone
Full-fledged Operations Start
100% SLA Ownership
Transition Planning &
Verification
Transition
Steady State
Duration will be finalized during transition planning for applications

## Slide 10: Transition Governance
Clearly laid out plan for Transition that will be approved by all stake holders and will be tracked closely by the TMO
Well defined KPIs and stage gate reviews to decide Go/ No-Go for next phase of transition or movement to steady state operations
Tracking of transition by logical grouping of applications / infra services & markets to ensure all streams of transition get the required attention
Periodic (Weekly) status meetings with markets and Regional Governance that will capture and track
  Progress of Transition
  Key Risks and Mitigations
  Key Issues
  KPI status
Escalation process and Governance Cadence for managing critical risks / show stoppers
Initiate change management process for aligning to the new service delivery model
Weekly Steering Committee update

## Slide 11: Transition Objectives By Phase
Transition Planning
Knowledge Transfer
Secondary Support
Primary Support
Key objectives:
Create detailed transition plan
Setup initial technical infrastructure
Create SME schedule
Develop detailed work stream plans
Sign off contract
Key objectives:
Acquire domain / technical / process knowledge from SME
Reverse present the knowledge back
Prepare Application Information Document (AID)
Key objectives:
Resolve historical / live tickets with SME’s help
Gain hands on experience on support process flow
Update AID
Key objectives:
Resolve live tickets independently
Kick off SLA baseline methodology
Establish plan for communication in Steady State

## Slide 12: Transition Planning Phase
Document Required KT Sessions
Get Sign-off of planned sessions from Avon and iSoftStone
Identify knowledge Providers and Consumers of knowledge in KT Phase
  Including time per session
Schedule sessions
  Knowledge Provider should spend time planning the session
    Relevant documentation
    Overview (Business/Technology and Historical Info)
    Tech Review:
      Issues
      CR’s
      Work In Progress
  Web Conference using iSoftStone conferencing to record for later viewing
TP
PS
SS
KT

## Slide 13: KT Phase
Market Unique KT
Business Process KT
Design & Architecture KT
Implementation KT
Reverse presentation
Mode of KT
Discussions
Documentation study
Code walkthrough
Applications Hands-on
Application Support KT
Application specific Support Process KT
Application Support Inventory & Metrics
Expectations from SMEs
“Dialogue”…not Q&A
Provide documentation
Review & validate understanding
Application Development KT
Application specific Development Process KT
Release Management Process
Acceptance Criteria
Application Information Document
Reverse presentation – Avon SME Signoff
TP
PS
SS
KT
Infrastructure Support KT
Infrastructure Support specific process KT
Infrastructure Inventory & Metrics

## Slide 14: KT Phase Tracking (SMT Example)
 |  |  | THIS PERIOD |  |  |  | BASELINE | FORECAST |  | CUMULATIVE |  |  | 
 |  |  | Forecast | Actual |  |  |  |  |  | Actual Through Current Period |  |  | 
Category | Planned Completion % | Actual Completion % |  | Completed | Rescheduled | Ineffective | Total | Total | To Complete | Total Meetings | Completed | Rescheduled (not yet reheld) | Ineffective (not yet reheld)
Finance | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order Capture | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order Fulfillment | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Field Management | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Avon Call Center | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
eCommerce | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reporting | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Master Data | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SAP Development | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Middleware (DS & PI) | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Basis | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SMT Methodology | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACC / Voice Integration | 0% | 0% |  |  |  |  |  |  |  |  |  |  | 
 | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 15: Post KT Session
KT Consumer has 2 business days to fill out the rating template
Attendees rate the session 1-5
Minimum rating of 3 required to validate the quality of the session
  If less than 3, remediation session will be scheduled
Reverse KT will be provided by the consumer back to Avon reflecting their understanding of the session
TP
PS
SS
KT

## Slide 16: KT Session Rating
Adequate time was allowed for conducting the KT sessions.
Functional knowledge relating to the application is explained and understood.
Operational knowledge relating to the application is explained and understood.
All non-core activities have been explained and understood.
The Application technical environment (e.g. Integrations, Infrastructure, Dependencies) has been explained and understood.
Technical knowledge relating to the application is explained and understood.
Business process / Business event knowledge relating to the application is explained and understood.
TP
PS
SS
KT

## Slide 17: Secondary Support
Hands-on
Impact Analysis
Low priority incident resolution
Mock incident resolution if required due to low volumes
End-of-period processes
Review of high priority incidents
Mode of Support
Independently handle low priority incidents
“Look-over-the-shoulder” for high priority incidents
Support Process
Establish Onsite/Offshore support process and PoC’s
Expectations from SMEs
Review & feedback on support activities
Joint walkthrough of complex code changes and bug-fixes done by incumbent team
Acceptance Criteria
Number of tickets addressed independently (TBD)
Key concerns coming out of KT can be implemented as an acceptance Criteria.
TP
PS
SS
KT

## Slide 18: Primary Support
Support
Independently handle most support Incidents
Mode of Support
Independently handle most support incidents
Avon SMEs available as back-up if required
Readiness Review
Review onsite & offshore infrastructure readiness
Review hardware/software readiness
Review steady state governance readiness
Review support process readiness
Ability to independently handle incidents
Expectations from SMEs
Review & feedback on support activities
Assist iSoftStone team in resolving incidents and requests, if escalated
Acceptance Criteria
Number of tickets resolved independently (TBD)
Key concerns coming out of Secondary Support can be implemented as an acceptance Criteria.
TP
PS
SS
KT

## Slide 19: Transition Management Structure
AVON Regional
Nilesh Patel
Karunakaran M.
Laurent Low
Martin Tsoi
Tan Yu Ting
Tan Yu Ting
AVON Global IT
Donagh Herlihy
Sue Liddie
Rollie Tadena
Erik Dillon
iSoftStone Regional
Anna xu
Linda Huang
TBD
Tower Mgr Samson Hu
App Lead Johnsen Zhang / William Feng
Execution
Leadership
Steering
Committee
iSoftStone Global
Program manager – Somnath Basu
Program
Management
Office
Transition
Management
Office

## Slide 20
Review process changes
Review cross- CoE issues
Review operational changes
Review areas for optimization
Review SLA’s
Review Work Order volumes
Review Demand Forecasts and Master Plans
Review Customer Satisfaction
Process Governance / Stakeholder Communication Meeting
Avon VMO Team
Avon Tower Leads
Avon PMO
iSoftStone Service Delivery
iSoftStone Tower Leads
SMEs as necessary
Review SLA & Performance Reports
Review resource issues
Conduct issue and risk resolution
Identify recommendations for SLA Changes
Determine Earn Back Tracking
Review Work Order approval issues
Review Work Order volumes
Create Demand Forecasts and Master Plans
Demand Management / Service Performance Meeting
Avon VMO Team
Avon Tower Leads
iSoftStone Service Delivery
iSoftStone Tower Leads
SMEs as necessary
Review iSoftStone performance
Resolve systemic issues
Resolve disputes
Review strategic plans
Review 12 mo. demand forecast
Review budget & issues
Discuss opportunities for innovation
Identify Continuous improvement
Senior Executive Steering Committee Meeting
Avon Executive Sponsor
Avon VMO Lead
Avon VMO Leadership
Avon CoE Leadership
Avon PMO
Strategic
Management
Operational
Strategy
Plans
Policies
Directives
Decisions
Dispute Resolution
Improvement Ideas
SLA Changes
Reporting
Financial Questions
Issue Escalation
Joint Communications
Avon
iSoftStone
Stakeholders
Other Providers
Joint Communications
Avon
iSoftStone
Stakeholders
Other Providers
Schedule
Every 4th Thursday of the month
VMO Steering Committee Meeting
Weekly
To be established through transition planning
Tower Meetings
Sr Executive Briefing
Every 6 months TBD
Process Gov
Every 2 weeks through transition, then as needed
Daily Work Order Review
Steady State Governance Structure

## Slide 21: Service Level Agreements based on Contract

## Slide 22: Case Study: SMT
Knowledge Transfer
Primary Support
280 Technology KT sessions completed
Secondary Support
96 Business KT sessions completed
14 workstreams
Average score of 4 / 5 for the KT sessions
141 tickets planned to be addressed
168 tickets addressed
77% tickets resolved independently against the target of 67%
93 tickets planned to be addressed
110 tickets addressed
99% independent resolution against the target of 96.8%
100% First time right resolution against target of 89%
Steady State – 04/07
Background
Complex OMS system built in SAP with eCommerce (Websphere commerce ) as the front-end for Canada market
Development effort of about 150+FTE for a duration of about 3 years
A very complex OMS system with multiple third party packages built on top of SAP systems
Entire Transition completed in less than 3 months
From 20th Jan 2014 to 7th Apr 2014

## Slide 23: Case Study: SMT
Hear it from the stakeholders

## Slide 24: Role of IT Lead
Ensure that local business commitments are met
  Provide local delivery
  Escalate issues, risks, and provide feedback to Transition Management Office as necessary
Keep local management informed
Assist in the Transition
  Coordinate time with SMEs
  Resolve resource schedule conflicts
Be the local change agent
Maintain a “Line of One”

## Slide 25: Next Steps
Date | Topic
June 24-26 | Market by market discussions
June 26-30 | Video Conferences between General Managers, Regional IT, VMO, and CIO
June 26 | Steering Committee update and final alignment
July 1-11 | Mobilize teams, establish SME’s and PoC’s Establish Transition Management Office and Governance committee
July 13- | Detailed Transition Planning Begins