## owssvr
Requestor | IT Responsible | Go Live | Remedy INC | Status | Business Requirements | CR Approval | Approval | Modified | Checked Out To | Collect Feedback | Comment | Content Type | Created | Created By | Deploy notification | Is Checked out to local | Est Effort (days) | File Size | ID | Modified By | Name | Priority | Remaining Effort | Title | Item Type | Path
Victoria Anderson/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002312943 | Pending Client Action |  |  |  | 2014-11-06 16:34 |  |  | Update coming 11/7/2014 | Document | 2014-09-15 11:19 | George Zhao/BKV/AU | 0 | 0 |  | 28677 | 148 | Josh Titley/BKV/AU | a text message to be sent out when an account reaches spur 3.docx | 2 |  | a text message to be sent out when an account reaches spur 3 | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | In Progress |  |  |  | 2014-11-20 09:54 |  |  |  | Document | 2014-11-20 09:53 | Giggs Liang/BKV/AU | 2 | 0 |  | 32612 | 185 | Giggs Liang/BKV/AU | Account Statement email change ACT.docx | 2 |  | Account Statement email change ACT | Item | sites/BKV2/process/Change Requests
Sarah Begg/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4153400% | INC000001708118 | Promoted Live |  | 16 |  | 2013-10-11 09:42 |  |  |  | Document | 2013-09-16 13:10 | Steve Bartlett/BKV/AU |  | 0 | 0.5 | 110592 | 54 | Steve Bartlett/BKV/AU | Add Country selector and Advertising recipient.doc | 2 |  | Add Country selector and Advertising recipient | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-11-03 16:55 |  |  |  | Document | 2014-10-24 16:39 | Giggs Liang/BKV/AU | 5 | 0 |  | 30172 | 172 | Giggs Liang/BKV/AU | Add validation to invalid address update.docx | 2 |  | Add validation to invalid address update | Item | sites/BKV2/process/Change Requests
Carly Coleman-Price/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002440987 | In Progress |  |  |  | 2013-12-18 14:44 |  |  |  | Document | 2013-12-18 14:44 | Ulrich Jensen/BKV/AU | 2 | 0 |  | 51200 | 97 | Ulrich Jensen/BKV/AU | Aging process changes.doc | 2 |  | Aging process changes | Item | sites/BKV2/process/Change Requests
Tyron Gyde | George Zhao/BKV/AU;#206 |  | INC000003024883 | UAT |  | 16 |  | 2014-10-24 10:44 |  |  |  | Document | 2014-10-13 11:41 | George Zhao/BKV/AU | 0 | 0 |  | 30236 | 163 | George Zhao/BKV/AU | ALSF reports change.docx | 2 |  | to exclude status 'PRE-REM' record frm ASLF reports | Item | sites/BKV2/process/Change Requests
Laure Belghiti/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC000003017575 | Promoted Live |  | 16 |  | 2014-10-17 14:57 |  |  |  | Document | 2014-10-10 16:26 | Giggs Liang/BKV/AU | 5 | 0 |  | 246386 | 159 | Giggs Liang/BKV/AU | ARIncident report add description field.docx | 2 |  | ARIncident report add description field | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4124600% | INC0000000000 | Promoted Live |  |  |  | 2012-12-10 15:37 |  |  |  | Document | 2012-12-05 14:04 | Steve Bartlett/BKV/AU | 2 | 0 |  | 57344 | 18 | Steve Bartlett/BKV/AU | ASLF Global KPI report changes - for merge.doc |  |  | ASLF Global KPI report changes | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4124600% | INC0000000000 | Promoted Live |  | 16 |  | 2012-12-10 15:36 |  |  |  | Document | 2012-11-27 09:28 | Steve Bartlett/BKV/AU | 2 | 0 |  | 57856 | 17 | Steve Bartlett/BKV/AU | ASLF Global KPI report changes.doc |  |  | ASLF Global KPI report changes | Item | sites/BKV2/process/Change Requests
Natalie Reid/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002867505 | Promoted Live |  | 16 |  | 2014-07-14 11:15 |  |  |  | Document | 2014-07-10 15:50 | George Zhao/BKV/AU | 0 | 0 | 1 | 239767 | 117 | George Zhao/BKV/AU | ASLF ranking report change request.docx | 2 |  | Sales Leadership Ranking by Year Report CR | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4157900% | project | Promoted Live |  |  |  | 2014-01-17 12:02 |  |  |  | Document | 2013-09-05 11:07 | Steve Bartlett/BKV/AU | 2 | 0 | 30 | 1670656 | 53 | Steve Bartlett/BKV/AU | ASLF report changes new sales model.doc | 1 | 100% | ASLF report changes new sales model | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | INC000002051781 | Promoted Live |  | 16 |  | 2013-02-21 10:07 |  |  |  | Document | 2013-01-31 09:21 | Steve Bartlett/BKV/AU |  | 0 |  | 58368 | 20 | Steve Bartlett/BKV/AU | ASLF report changes.doc |  |  | ASLF report changes | Item | sites/BKV2/process/Change Requests
Ulrich Jensen/BKV/AU | George Zhao/BKV/AU;#206 |  | 00000 | In Progress |  | 16 |  | 2014-11-25 10:27 |  |  |  | Document | 2014-11-25 10:27 | George Zhao/BKV/AU |  | 0 |  | 29191 | 186 | George Zhao/BKV/AU | Aussie Adapter CR2 of Award Points.docx | 2 |  | Aussie Adapter CR2 of Award Points | Item | sites/BKV2/process/Change Requests
Ulrich Jensen/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000001708118 | Promoted Live |  | 16 |  | 2014-11-11 09:04 |  |  |  | Document | 2014-10-31 16:31 | George Zhao/BKV/AU |  | 0 |  | 37458 | 176 | George Zhao/BKV/AU | AussieAdapter CR of Award points.docx | 2 |  | AussieAdapter CR of Award points | Item | sites/BKV2/process/Change Requests
Carly Coleman-Price/BKV/AU | George Zhao/BKV/AU;#206 | 4146400% | INC000002292427 | Promoted Live |  | 16 |  | 2013-08-05 10:47 |  |  |  | Document | 2013-07-09 12:29 | George Zhao/BKV/AU | 2 | 0 | 1 | 48770 | 48 | Steve Bartlett/BKV/AU | Bad Debt query Form.docx | 1 | 1% | Bad Debt query Form | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4116200% | CRQ000000061889 | Promoted Live |  |  |  | 2012-09-12 15:20 |  |  |  | Document | 2012-09-05 14:52 | Steve Bartlett/BKV/AU |  | 0 |  | 54272 | 6 | Steve Bartlett/BKV/AU | Bad debt rule change for sales leadership.doc |  |  | Bad debt rule change for sales leadership | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-07-28 10:52 |  |  |  | Document | 2014-07-22 16:21 | Giggs Liang/BKV/AU |  | 0 |  | 30932 | 124 | Giggs Liang/BKV/AU | Batch of bug fix and improvement.docx | 2 |  | Batch of bug fix and improvement in order processor and completer | Item | sites/BKV2/process/Change Requests
Katharine Aitken/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC | Promoted Live |  | 16 |  | 2014-11-12 09:46 |  |  |  | Document | 2014-11-03 16:56 | Giggs Liang/BKV/AU | 2 | 0 | 2 | 133918 | 178 | Giggs Liang/BKV/AU | Blacklist rep to specific account and invalid shipping name fix.docx | 2 |  | Blacklist rep to specific account and invalid shipping name fix | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | Josh Titley/BKV/AU;#47 |  | N/A | Analysis/Development |  |  | 15 | 2014-10-28 14:50 |  |  | Now with Global | Document | 2014-10-20 15:16 | Josh Titley/BKV/AU | 2 | 0 |  | 227328 | 168 | Josh Titley/BKV/AU | BRANZ62ANZ Customer Order Improvements For DCE.doc | 2 |  | Custer Order Improvements For DCE | Item | sites/BKV2/process/Change Requests
Roger Peisley/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC000003099137 | In Progress |  |  |  | 2014-12-01 10:39 |  |  |  | Document | 2014-12-01 10:38 | Giggs Liang/BKV/AU | 2 | 0 |  | 47174 | 188 | Giggs Liang/BKV/AU | Bug fix - Bulk mailer error message.docx | 2 |  | Bug fix - Bulk mailer error message | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-08-13 09:42 |  |  |  | Document | 2014-08-12 11:22 | Giggs Liang/BKV/AU |  | 0 |  | 28989 | 131 | Giggs Liang/BKV/AU | Bug fix on address validation.docx | 1 |  | Bug fix on address validation | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-09-10 09:32 |  |  |  | Document | 2014-09-09 11:28 | Giggs Liang/BKV/AU |  | 0 |  | 131007 | 141 | Giggs Liang/BKV/AU | Bug fix on reporting by order placed datetime instead of order received.docx | 2 |  | Bug fix on reporting by order placed datetime instead of order received | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-09-11 15:37 |  |  |  | Document | 2014-09-09 15:58 | Giggs Liang/BKV/AU |  | 0 |  | 30183 | 142 | Giggs Liang/BKV/AU | Bug fix on SICS Dialogue.docx | 2 |  | Bug fix on SICS Dialogue | Item | sites/BKV2/process/Change Requests
Carolyn Doig/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4134100% | INC000002015316 | Promoted Live |  | 16 |  | 2013-03-13 11:30 |  |  |  | Document | 2013-03-06 16:39 | Steve Bartlett/BKV/AU |  | 0 |  | 670208 | 26 | Steve Bartlett/BKV/AU | Bulk email reply to address.doc |  |  | bulk email replyto address | Item | sites/BKV2/process/Change Requests
Roger Peisley/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002414644 | Promoted Live |  | 17 |  | 2014-07-30 14:34 |  |  | Consolidated of the following tickets: INC000002414644 INC000002414646 INC000002614354 INC000002619268 INC000002639300 Requirements still a bit sparse. Need some screenshots so we see what the new functionality will look like. | Document | 2014-04-29 15:49 | Josh Titley/BKV/AU | 2 | 0 | 50 | 104230 | 107 | Josh Titley/BKV/AU | Bulk Emailer Changes.docx | 2 | 50% | Multiple Enhancements To Bulk Emailer | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4119100% | INC000001889975 | Promoted Live |  | 16 |  | 2012-10-09 10:05 |  |  |  | Document | 2012-10-09 09:12 | Steve Bartlett/BKV/AU |  | 0 |  | 53248 | 8 | Steve Bartlett/BKV/AU | Cannot access historical Earning statements.doc |  |  | Cannot access historical Earning statements | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4120000% | INC000001940459 | Promoted Live |  | 16 |  | 2012-11-06 14:07 |  |  |  | Document | 2012-10-18 10:52 | Steve Bartlett/BKV/AU |  | 0 |  | 112640 | 11 | Steve Bartlett/BKV/AU | Cannot convert Earning Statements into an excel format.doc |  |  | Cannot convert Earning Statements into an excel format | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC0000000000 | Analysis/Development |  |  |  | 2014-09-15 12:37 |  |  |  | Document | 2014-09-10 12:19 | Josh Titley/BKV/AU | 2 | 0 |  | 578560 | 143 | Josh Titley/BKV/AU | Canon Invoice Support.doc | 3 |  | Canon Invoice Support | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | George Zhao/BKV/AU;#206 |  | 000000 | In Progress |  | 16 |  | 2014-10-31 15:26 |  |  |  | Document | 2014-10-31 15:18 | George Zhao/BKV/AU | 0 | 0 |  | 41012 | 175 | George Zhao/BKV/AU | Carton Allocator CR.docx | 2 |  | Carton Allocator CR | Item | sites/BKV2/process/Change Requests
Susanne Groves/BKV/AU | George Zhao/BKV/AU;#206 | 4136800% | INC000002143873 | Promoted Live |  | 16 |  | 2013-04-09 10:30 |  |  |  | Document | 2013-04-04 10:44 | George Zhao/BKV/AU |  | 0 |  | 95232 | 32 | Steve Bartlett/BKV/AU | change one of the lead sources in PR site.doc | 2 |  | change one of the lead sources in PR site | Item | sites/BKV2/process/Change Requests
Katharine Aitken/BKV/AU | Josh Titley/BKV/AU;#47 |  | N/A | In Progress | 15 |  |  | 2014-10-22 11:45 |  |  |  | Document | 2014-10-22 11:40 | Josh Titley/BKV/AU | 2 | 0 |  | 29694 | 169 | Josh Titley/BKV/AU | Change eBrochure Routing For DSMs.docx | 2 |  | Change eBrochure Routing For DSMs | Item | sites/BKV2/process/Change Requests
Adrian Diebold/BKV/AU | George Zhao/BKV/AU;#206 | 4123600% | INC000001981285 | Promoted Live |  |  |  | 2012-11-23 14:39 |  |  |  | Document | 2012-11-21 17:40 | George Zhao/BKV/AU | 2 | 0 |  | 28333 | 15 | Steve Bartlett/BKV/AU | Change Enhancement required to PDF Download web-tool.docx |  |  | Change/Enhancement required to PDF Download web-tool | Item | sites/BKV2/process/Change Requests
Susan Bonanno/BKV/AU | George Zhao/BKV/AU;#206 | 4144242% | INC000002248964 | Promoted Live |  |  |  | 2013-06-28 12:47 |  |  |  | Document | 2013-06-14 16:27 | George Zhao/BKV/AU | 2 | 0 | 1 | 51200 | 43 | George Zhao/BKV/AU | change of name of Benjamin H Riley in happy birday letter.doc | 1 | 1% | change of name of Benjamin H Riley in happy birday letter | Item | sites/BKV2/process/Change Requests
Susan Bonanno/BKV/AU | George Zhao/BKV/AU;#206 | 4144242% | INC000002248964 | Promoted Live |  | 16 |  | 2013-06-28 12:53 |  |  |  | Document | 2013-06-14 16:28 | George Zhao/BKV/AU | 2 | 0 | 1 | 26485 | 44 | George Zhao/BKV/AU | change of name of Benjamin H Riley in happy birday letter.docx | 1 | 1% | change of name of Benjamin H Riley in happy birday letter | Item | sites/BKV2/process/Change Requests
Joy Soriano/BKV/AU | Chris Anscomb/BKV/AU;#167 |  | INC000002536144 | In Progress |  |  | 2 | 2014-01-09 14:42 |  |  |  | Document | 2014-01-09 14:42 | Ulrich Jensen/BKV/AU |  | 0 |  | 50176 | 103 | Ulrich Jensen/BKV/AU | Changes to FSP reports.doc | 2 |  | Changes to FSP reports | Item | sites/BKV2/process/Change Requests
Istvan Kertesz/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000001625519 | Cancelled | 2 |  |  | 2014-10-07 14:27 |  |  |  | Document | 2013-04-09 10:40 | David Hoschke/BKV/AU | 0 | 0 |  | 52224 | 33 | David Hoschke/BKV/AU | Changes to tentative Master schedule.doc | 3 |  | Changes to tentative Master schedule | Item | sites/BKV2/process/Change Requests
Rod Hovell/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000002237595 | In Progress |  |  |  | 2013-12-17 16:04 |  |  |  | Document | 2013-12-17 16:03 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 50176 | 93 | Ulrich Jensen/BKV/AU | Code changes in MacPac to update WMS.doc | 2 |  | Code changes in MacPac to update WMS | Item | sites/BKV2/process/Change Requests
Stephen McCormack/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002994115 | In Progress |  |  |  | 2014-10-20 14:33 |  |  |  | Document | 2014-10-20 14:33 | George Zhao/BKV/AU | 0 | 0 |  | 26652 | 167 | George Zhao/BKV/AU | convert Paris letters to be used with Mail Merge instead.docx | 2 |  | convert Paris letters to be used with Mail Merge instead | Item | sites/BKV2/process/Change Requests
Anthony Irwin/BKV/AU | George Zhao/BKV/AU;#206 | 4136400% | INC000002109312 | Promoted Live |  | 16 |  | 2014-04-30 15:11 |  |  |  | Document | 2013-03-05 11:56 | Steve Bartlett/BKV/AU |  | 0 |  | 77824 | 24 | Josh Titley/BKV/AU | COT Online trending.doc | 2 |  | COT online trending | Item | sites/BKV2/process/Change Requests
Victoria Anderson/BKV/AU | George Zhao/BKV/AU;#206 |  | Step | Promoted Live |  | 16 |  | 2014-09-29 08:53 |  |  |  | Document | 2014-09-26 14:24 | George Zhao/BKV/AU | 0 | 0 | 1 | 57400 | 152 | George Zhao/BKV/AU | CR email look up includes non email rep.docx | 2 |  | CR email look up includes non email rep | Item | sites/BKV2/process/Change Requests
Victoria Anderson/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002032263 | In Progress |  |  |  | 2013-11-22 14:45 |  |  |  | Document | 2013-11-22 14:44 | Ulrich Jensen/BKV/AU |  | 0 |  | 50176 | 67 | Ulrich Jensen/BKV/AU | Credit review – Display credit held invoices.doc | 2 |  | Credit review - Display credit held invoices | Item | sites/BKV2/process/Change Requests
Carly Coleman-Price/BKV/AU | Hans Logeman/BKV/AU;#399 |  | INC000001813054 | Promoted Live |  |  |  | 2014-10-07 14:32 |  |  |  | Document | 2013-12-17 08:49 | Ulrich Jensen/BKV/AU | 2 | 0 |  | 54272 | 82 | David Hoschke/BKV/AU | Credits for brochures purchased under ASLF.doc | 2 |  | Credits for brochures purchased under ASLF | Item | sites/BKV2/process/Change Requests
Douglas Powley/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC000003088417 | In Progress |  |  |  | 2014-11-18 09:22 |  |  |  | Document | 2014-11-18 09:22 | Giggs Liang/BKV/AU | 2 | 0 |  | 89549 | 183 | Giggs Liang/BKV/AU | Critical Monitoring run in Windows8.docx | 2 |  | Critical Monitoring run in Windows8 | Item | sites/BKV2/process/Change Requests
Adrian Diebold/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002310039 | Analysis/Development | 2 |  |  | 2013-10-10 17:09 |  |  |  | Document | 2013-10-10 16:59 | Ulrich Jensen/BKV/AU | 2 | 0 |  | 27084 | 59 | Ulrich Jensen/BKV/AU | Critical Monitoring.docx | 2 |  | Critical Monitoring | Item | sites/BKV2/process/Change Requests
Istvan Kertesz/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000001792254 | Promoted Live |  |  |  | 2014-10-07 14:32 |  |  |  | Document | 2013-12-17 08:33 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 302080 | 81 | David Hoschke/BKV/AU | Critical Stock Freeze Report as Excel file.doc | 2 |  | Critical Stock Freeze Report as Excel file | Item | sites/BKV2/process/Change Requests
Victoria Anderson/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000001708118 | Promoted Live |  | 16 |  | 2014-09-15 13:58 |  |  |  | Document | 2014-07-31 14:34 | George Zhao/BKV/AU | 0 | 0 | 1.5 | 114040 | 127 | George Zhao/BKV/AU | csintranent email lookup CR.docx | 2 | 1.5% | csintranent email lookup CR | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Analysis/Development |  |  |  | 2014-11-19 09:05 |  |  |  | Document | 2014-11-04 09:45 | Giggs Liang/BKV/AU | 2 | 0 |  | 220029 | 179 | Giggs Liang/BKV/AU | Customer History in ZMSuite.docx | 2 |  | Customer History in ZMSuite | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000001708118 | Analysis/Development |  |  |  | 2014-10-28 14:49 |  |  | Not a priority at the moment | Document | 2014-07-11 15:42 | George Zhao/BKV/AU | 0 | 0 | 5 | 28753 | 121 | Josh Titley/BKV/AU | DAR Change - See Downline Downlines Activity.docx | 3 | 5% | INC000002702543 | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-07-28 10:52 |  |  |  | Document | 2014-07-17 10:33 | Giggs Liang/BKV/AU |  | 0 |  | 135575 | 123 | Giggs Liang/BKV/AU | DCE Data Import Tools.docx | 2 |  | DCE Data Import Tools | Item | sites/BKV2/process/Change Requests
Anthony Irwin/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000001900930 | Promoted Live |  |  | 2 | 2014-10-07 14:35 |  |  |  | Document | 2013-12-18 13:36 | Ulrich Jensen/BKV/AU |  | 0 |  | 53760 | 95 | David Hoschke/BKV/AU | Demand changes in MacPac.doc | 2 |  | Demand changes in MacPac | Item | sites/BKV2/process/Change Requests
Rod Hovell/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000002111143 | Pending Client Action |  |  |  | 2013-12-17 15:00 |  |  |  | Document | 2013-12-17 14:55 | Ulrich Jensen/BKV/AU |  | 0 |  | 49664 | 87 | Ulrich Jensen/BKV/AU | DHL Critical Stock report.doc | 2 |  | DHL Critical Stock report | Item | sites/BKV2/process/Change Requests
Istvan Kertesz/BKV/AU | Steve Bartlett/BKV/AU;#48;#David Hoschke/BKV/AU;#170 |  | INC000002109279 | Promoted Live |  |  |  | 2014-10-07 14:27 |  |  |  | Document | 2013-03-28 10:59 | David Hoschke/BKV/AU | 0 | 0 |  | 71168 | 30 | David Hoschke/BKV/AU | DHL EDI Phase 1 - open order report.doc | 1 |  | Macpac/DHL EDI inteface part1 | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | UAT |  | 4 |  | 2014-10-07 15:14 |  |  |  | Document | 2014-10-01 10:20 | Giggs Liang/BKV/AU | 2 | 0 |  | 31160 | 153 | Giggs Liang/BKV/AU | Direct Delivery Activity Report Changes 2.docx | 2 |  | Direct Delivery Activity Report Changes | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-08-26 15:20 |  |  |  | Document | 2014-08-25 09:27 | Giggs Liang/BKV/AU |  | 0 |  | 430617 | 133 | Giggs Liang/BKV/AU | Direct Delivery Activity Report Changes.docx | 2 |  | Direct Delivery Activity Report Changes | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | None | Cancelled |  |  |  | 2013-06-04 15:49 |  |  | No longer required | Document | 2013-06-04 11:17 | Steve Bartlett/BKV/AU | 2 | 0 |  | 53248 | 42 | Steve Bartlett/BKV/AU | Downline Activity report for ARLs.doc | 2 |  | Downline Activity report for ARLs | Item | sites/BKV2/process/Change Requests
Noni White | Steve Bartlett/BKV/AU;#48 | 4138300% | INC000001708118 | Cancelled |  |  |  | 2014-05-07 15:32 |  |  |  | Document | 2013-04-16 10:33 | Steve Bartlett/BKV/AU | 2 | 0 |  | 52224 | 36 | Josh Titley/BKV/AU | Downline activity report Order placed value.doc | 2 |  | Downline activity report Order placed value | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-09-10 09:32 |  |  |  | Document | 2014-08-22 16:51 | Giggs Liang/BKV/AU | 2 | 0 |  | 207555 | 132 | Giggs Liang/BKV/AU | DSM Direct Delivery Activity Report.docx | 2 |  | DSM Direct Delivery Activity Report | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-09-09 11:30 |  |  |  | Document | 2014-09-04 10:20 | Giggs Liang/BKV/AU |  | 0 |  | 30009 | 139 | Giggs Liang/BKV/AU | Duplicated order approve and decline process.docx | 2 |  | Duplicated order approve and decline process | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-08-27 17:06 |  |  |  | Document | 2014-08-26 15:21 | Giggs Liang/BKV/AU |  | 0 |  | 29384 | 135 | Giggs Liang/BKV/AU | Duplicated order check and batch of bug fix.docx | 2 |  | Duplicated order check and batch of bug fix | Item | sites/BKV2/process/Change Requests
Stephen Freestone/BKV/AU | George Zhao/BKV/AU;#206 | 4145800% | 0000000000 | Promoted Live |  | 16 |  | 2013-08-05 10:46 |  |  | T | Document | 2013-07-02 15:32 | George Zhao/BKV/AU | 2 | 0 | 3 | 83647 | 46 | Steve Bartlett/BKV/AU | email invoice to no picks rep.docx | 1 | 0% | email invoice to no picks rep | Item | sites/BKV2/process/Change Requests
Stephen Freestone/BKV/AU | George Zhao/BKV/AU;#206 | 4145842% | 0000000000 | Promoted Live |  |  |  | 2013-07-04 10:48 |  |  | Ticket Completed | Document | 2013-07-04 10:48 | Stephen Freestone/BKV/AU | 2 | 0 | 3 | 83649 | 47 | Stephen Freestone/BKV/AU | email invoice to no picks rep_completed.docx | 1 | 0% | email invoice to no picks rep | Item | sites/BKV2/process/Change Requests
Victoria Anderson/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002027169 | Cancelled |  |  |  | 2014-11-10 10:20 |  |  | 10.11.2015 - Cancelled At Victoria's Request | Document | 2014-09-15 11:31 | George Zhao/BKV/AU | 0 | 0 |  | 29842 | 149 | Josh Titley/BKV/AU | Email Manager Held Warning.docx | 2 |  | Email Manager Held Warning | Item | sites/BKV2/process/Change Requests
Victoria Anderson/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4136200% | INC000002101517 | Cancelled |  |  |  | 2013-03-18 11:21 |  |  |  | Document | 2013-02-27 08:58 | Steve Bartlett/BKV/AU | 2 | 0 |  | 50688 | 23 | Steve Bartlett/BKV/AU | Email Rep when an item is manually shorted.doc |  |  | Email Rep when an item is manually shorted | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | George Zhao/BKV/AU;#206 | 4182300% | INC000002707746 | Promoted Live |  | 16 |  | 2014-07-02 10:50 |  |  |  | Document | 2014-06-30 17:34 | George Zhao/BKV/AU | 0 | 0 | 1 | 62482 | 114 | George Zhao/BKV/AU | eminifest do not saving the email before the sending.docx | 2 | 1% | e-manifest- saving the changes prior prior to the sending of the data | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | In Progress |  |  |  | 2014-11-21 16:43 |  |  |  | Document | 2014-11-19 09:43 | Giggs Liang/BKV/AU | 2 | 0 |  | 1638879 | 184 | Giggs Liang/BKV/AU | eParcel SICS XML change.docx | 2 |  | eParcel SICS XML change | Item | sites/BKV2/process/Change Requests
Michael Anderson/BKV/AU | George Zhao/BKV/AU;#206 |  | 0000000 | Promoted Live |  | 16 |  | 2014-09-09 09:29 |  |  |  | Document | 2014-08-06 16:39 | George Zhao/BKV/AU | 0 | 0 | 1.5 | 65232 | 130 | George Zhao/BKV/AU | error check weight 99999 issue.docx | 2 |  | error check weight 99999 issue | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC | Promoted Live |  | 16 |  | 2014-07-03 10:56 |  |  |  | Document | 2014-06-30 12:03 | Giggs Liang/BKV/AU |  | 0 | 2 | 30706 | 112 | Giggs Liang/BKV/AU | Fix blacklist issue and centralization.docx | 2 |  | Fix blacklist issue and centralization | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC | Promoted Live |  | 16 |  | 2014-07-03 10:56 |  |  |  | Document | 2014-06-30 11:20 | Giggs Liang/BKV/AU |  | 0 | 2 | 30909 | 111 | Giggs Liang/BKV/AU | Fix Husky Order duplicated Return Number.docx | 2 |  | Fix Husky Order duplicated Return Number | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | George Zhao/BKV/AU;#206 | 4138200% | 00000000000 | Promoted Live |  | 16 |  | 2013-06-28 13:06 |  |  |  | Document | 2013-04-17 16:25 | George Zhao/BKV/AU |  | 0 |  | 54784 | 37 | George Zhao/BKV/AU | FMR Implementation.doc | 2 |  | FMR Implementation | Item | sites/BKV2/process/Change Requests
Roger Peisley/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002768982 | Promoted Live |  | 16 |  | 2014-09-15 15:30 |  |  | Waiting On Business Requirement | Document | 2014-07-11 10:50 | Josh Titley/BKV/AU | 2 | 0 |  | 29841 | 118 | George Zhao/BKV/AU | Form Builder Postcode Changes.docx | 2 |  | Notification of Severity of incoming complaints and adverse reactions | Item | sites/BKV2/process/Change Requests
Joy Soriano/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002510949 | In Progress |  |  | 2 | 2013-11-28 09:45 |  |  |  | Document | 2013-11-28 09:43 | Ulrich Jensen/BKV/AU |  | 0 |  | 50176 | 69 | Ulrich Jensen/BKV/AU | FSP report – Add new column for history pages.doc | 2 |  | FSP report - Add new column for history pages | Item | sites/BKV2/process/Change Requests
Augustin Leung/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000001787279 | In Progress |  |  |  | 2013-12-09 16:18 |  |  |  | Document | 2013-12-09 16:17 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 50176 | 78 | Ulrich Jensen/BKV/AU | Goods receipt always against a PO.doc | 2 |  | Goods receipt always against a PO | Item | sites/BKV2/process/Change Requests
Anthony Irwin/BKV/AU | Chris Rickards/BKV/AU;#71 |  | INC000002271282 | Promoted Live |  |  | 2 | 2014-10-07 14:33 |  |  |  | Document | 2013-12-17 15:31 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 54784 | 89 | David Hoschke/BKV/AU | GST and NTA calculations for Set billing.doc | 2 |  | GST and NTA calculations for Set billing | Item | sites/BKV2/process/Change Requests
Nichole McLachlan/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | INC000002529899 | Cancelled |  |  |  | 2014-07-30 14:29 |  |  |  | Document | 2014-01-14 11:02 | Steve Bartlett/BKV/AU | 6 | 0 |  | 53760 | 104 | Josh Titley/BKV/AU | Hot leads Form builder enhancement.doc | 2 |  | Hot leads Form builder enhancement | Item | sites/BKV2/process/Change Requests
David Hoschke/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | Husky | Cancelled |  |  |  | 2014-04-30 15:05 |  |  |  | Document | 2013-06-20 12:03 | Steve Bartlett/BKV/AU | 2 | 0 |  | 93696 | 45 | Josh Titley/BKV/AU | Husky - SICS - AS400.doc | 1 |  | Husky - SICS - AS400 integration | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | Husky | Cancelled |  |  |  | 2014-04-30 15:04 |  |  |  | Document | 2013-05-20 14:34 | Steve Bartlett/BKV/AU | 2 | 0 |  | 189440 | 40 | Josh Titley/BKV/AU | Husky - SICS.doc | 1 |  | Husky - SICS | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | Husky | Promoted Live |  |  |  | 2014-04-30 15:09 |  |  |  | Document | 2013-10-14 12:05 | Steve Bartlett/BKV/AU | 2 | 0 |  | 53248 | 61 | Josh Titley/BKV/AU | Husky Activity report.doc | 2 |  | Husky Activity report | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | Husky | Cancelled |  |  |  | 2014-04-30 15:11 |  |  |  | Document | 2013-11-01 15:58 | Steve Bartlett/BKV/AU | 2 | 0 |  | 52736 | 65 | Josh Titley/BKV/AU | Husky alternate carrier.doc | 2 |  | Husky alternate carrier | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | George Zhao/BKV/AU;#206 |  | 0000000000 | Promoted Live |  | 16 |  | 2014-04-30 15:08 |  |  |  | Document | 2013-11-28 16:34 | George Zhao/BKV/AU | 0 | 0 | 1 | 57582 | 70 | Josh Titley/BKV/AU | Husky late to start reports.docx | 2 | 1% | Husky late to start reports | Item | sites/BKV2/process/Change Requests
George Zhao/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002968235 | Promoted Live |  | 16 |  | 2014-09-10 14:49 |  |  |  | Document | 2014-09-04 16:05 | George Zhao/BKV/AU |  | 0 | 1 | 30048 | 140 | Josh Titley/BKV/AU | husky order address has extra 9 in address 2 field.docx | 2 |  | husky order address has extra 9 in address 2 field | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | 12345 | Promoted Live |  |  |  | 2014-04-30 15:12 |  |  | Option 103 in SICS menu | Document | 2013-12-12 16:29 | Kyle Wilkinson/BKV/AU | 0 | 0 |  | 25288 | 79 | Josh Titley/BKV/AU | Husky order complete program option 103 SICS Menu.docx | 2 |  | Husky Order complete program | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC000003110272 | In Progress |  |  |  | 2014-12-01 11:40 |  |  |  | Document | 2014-12-01 11:25 | Giggs Liang/BKV/AU | 2 | 0 |  | 71854 | 189 | Giggs Liang/BKV/AU | Husky Order Traffic Code picking.docx | 2 |  | Husky Order Traffic Code picking | Item | sites/BKV2/process/Change Requests
Michael Anderson/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | Husky | Promoted Live | 2 |  |  | 2014-04-30 15:08 |  |  |  | Document | 2013-11-28 16:45 | Steve Bartlett/BKV/AU | 0 | 0 |  | 90624 | 71 | Josh Titley/BKV/AU | Husky Picking data Inquiry changes.doc | 2 |  | Husky Picking Data inquiry change | Item | sites/BKV2/process/Change Requests
Carl Mogridge/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 4 | 15 | 2014-11-14 10:58 |  |  |  | Document | 2014-09-11 15:39 | Giggs Liang/BKV/AU | 4 | 0 |  | 6208981 | 144 | Giggs Liang/BKV/AU | Husky Reporting - Phase 1.docx | 2 |  | Husky Reporting - Phase 1 | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | Husky | Promoted Live |  |  |  | 2014-04-30 15:08 |  |  |  | Document | 2013-12-03 12:50 | Steve Bartlett/BKV/AU | 0 | 0 |  | 55296 | 74 | Josh Titley/BKV/AU | Husky SICS Label changes.doc | 2 |  | Husky SICS Label changes | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | George Zhao/BKV/AU;#206 |  | 0000000000 | Promoted Live |  | 16 |  | 2014-04-30 15:08 |  |  |  | Document | 2013-12-02 15:41 | George Zhao/BKV/AU | 0 | 0 | 1 | 57662 | 73 | Josh Titley/BKV/AU | Husky start Order report.docx | 2 | 1% | Husky start Order report | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | George Zhao/BKV/AU;#206 | 4173900% | 0000000 | Promoted Live |  | 16 |  | 2014-05-07 15:31 |  |  |  | Document | 2014-04-08 10:04 | Kyle Wilkinson/BKV/AU |  | 0 |  | 32267 | 106 | Josh Titley/BKV/AU | Husky traffic code divert criteria_Apr14.docx | 2 |  | Husky traffic code diverts | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | Husky | Promoted Live |  | 16 |  | 2014-04-30 15:05 |  |  |  | Document | 2013-08-14 14:40 | Steve Bartlett/BKV/AU |  | 0 | 2 | 54784 | 51 | Josh Titley/BKV/AU | Husky traffic codes.doc | 2 |  | Husky traffic codes | Item | sites/BKV2/process/Change Requests
Shane Dos Ramos | George Zhao/BKV/AU;#206 |  | INC000002885398 | Cancelled |  |  |  | 2014-10-20 15:44 |  |  | Waited two months for Business Requirement. Cancelled. | Document | 2014-09-15 10:54 | Josh Titley/BKV/AU | 2 | 0 |  | 28816 | 146 | Josh Titley/BKV/AU | Improve Returned Goods Process.docx | 3 |  | Improve Return Goods Process | Item | sites/BKV2/process/Change Requests
Roger Peisley/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4141800% | INC000002119369 | Promoted Live |  |  |  | 2013-05-29 16:41 |  |  |  | Document | 2013-05-10 12:01 | Steve Bartlett/BKV/AU |  | 0 | 2 | 166400 | 39 | Steve Bartlett/BKV/AU | Insermo mailout integration.doc | 2 | 5% | Insermo mailout integration | Item | sites/BKV2/process/Change Requests
Victoria Anderson/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | Project Stork | Promoted Live |  | 16 |  | 2013-05-08 16:04 |  |  |  | Document | 2013-03-25 16:24 | Steve Bartlett/BKV/AU |  | 0 |  | 74240 | 29 | Steve Bartlett/BKV/AU | Instant delivery picking slip change.doc | 2 |  | Instant delivery picking slip change | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002955533 | Pending Client Action |  | 16 |  | 2014-10-31 15:21 |  |  |  | Document | 2014-10-24 10:36 | George Zhao/BKV/AU |  | 0 |  | 50025 | 171 | George Zhao/BKV/AU | Leaving Line Number Field in Replacements is not performing product lookup.docx | 2 |  | Leaving Line Number Field in Replacements is not performing product lookup. | Item | sites/BKV2/process/Change Requests
Stephen McCormack/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4136100% | INC000002039837 | Promoted Live |  | 16 |  | 2013-03-28 15:05 |  |  |  | Document | 2013-03-18 17:05 | Jennifer Hulme/BKV/AU | 2 | 0 |  | 49664 | 27 | Steve Bartlett/BKV/AU | Line 3_5_7 FSC Usage.doc | 2 |  | Line 3/5/7 FSC Usage | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-10-08 11:01 |  |  |  | Document | 2014-10-07 15:14 | Giggs Liang/BKV/AU | 5 | 0 |  | 101010 | 156 | Giggs Liang/BKV/AU | Log Invoice printed datetime in Husky Console.docx | 2 |  | Log Invoice printed datetime in Husky Console | Item | sites/BKV2/process/Change Requests
Tyron Gyde | George Zhao/BKV/AU;#206 |  | INC000001708118 | Promoted Live |  | 16 |  | 2014-08-19 16:18 |  |  |  | Document | 2014-08-05 12:54 | George Zhao/BKV/AU | 0 | 0 |  | 742129 | 129 | George Zhao/BKV/AU | LOS2 bonus reporting.docx | 2 |  | Notification of Severity of incoming complaints and adverse reactions | Item | sites/BKV2/process/Change Requests
Zack Yang/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4116200% | INC000001878388 | Promoted Live |  | 16 |  | 2012-09-12 10:36 |  |  |  | Document | 2012-09-10 09:54 | Steve Bartlett/BKV/AU |  | 0 |  | 53248 | 7 | Steve Bartlett/BKV/AU | Mailout program access control.doc |  |  | Mailout program access control | Item | sites/BKV2/process/Change Requests
Rod Hovell/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | INC000001850254 | Promoted Live |  | 16 |  | 2013-03-13 11:30 |  |  |  | Document | 2013-02-26 10:38 | Steve Bartlett/BKV/AU |  | 0 |  | 51712 | 21 | Steve Bartlett/BKV/AU | manual shorts drop out when locations are moved.doc |  |  | Manual shorts drop out when locations are changed | Item | sites/BKV2/process/Change Requests
Adrian Diebold/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000001836314 | Pending Client Action |  |  | 2 | 2013-12-17 12:46 |  |  |  | Document | 2013-12-17 09:39 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 50688 | 84 | Ulrich Jensen/BKV/AU | Manufacturing Order Demands inclusion.doc | 2 |  | Manufacturing Order Demands | Item | sites/BKV2/process/Change Requests
Adrian Diebold/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4120000% | INC000001864908 | Promoted Live |  | 16 |  | 2012-11-12 10:40 |  |  |  | Document | 2012-10-17 12:08 | Steve Bartlett/BKV/AU |  | 0 |  | 57856 | 10 | George Zhao/BKV/AU | Manufacturing order demands.doc |  |  | Manufacturing order demand - must be included in Demand reportand adverse reactions | Item | sites/BKV2/process/Change Requests
Jenni Lampard/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | N/A | In Progress | 2 |  |  | 2014-06-18 16:44 |  |  |  | Document | 2014-06-18 16:44 | Jennifer Hulme/BKV/AU |  | 0 |  | 26259 | 109 | Jennifer Hulme/BKV/AU | Menu change with Authorisations for Order Processing.docx | 3 |  | Menu change with Authorisations for Order Processing | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | George Zhao/BKV/AU;#206 |  | 00000000 | Promoted Live |  | 16 |  | 2014-04-30 15:12 |  |  |  | Document | 2013-11-27 14:32 | George Zhao/BKV/AU | 0 | 0 | 1 | 89131 | 68 | Josh Titley/BKV/AU | Missing shipper report for husky customer.docx | 2 | 1% | Missing shipper report for husky customer | Item | sites/BKV2/process/Change Requests
Giggs Liang/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-09-09 11:30 |  |  |  | Document | 2014-09-01 15:31 | Giggs Liang/BKV/AU |  | 0 |  | 31077 | 137 | Giggs Liang/BKV/AU | MIT Upload tools bug fix and husky console log.docx | 2 |  | MIT Upload tools bug fix and husky console log | Item | sites/BKV2/process/Change Requests
Anthony Irwin/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-10-21 14:54 |  |  |  | Document | 2014-10-01 11:14 | Giggs Liang/BKV/AU | 5 | 0 |  | 30686 | 155 | Giggs Liang/BKV/AU | MIT upload validation on brand and FSC field.docx | 2 |  | MIT upload validation on brand and FSC field | Item | sites/BKV2/process/Change Requests
Ulrich Jensen/BKV/AU | George Zhao/BKV/AU;#206 | 4147000% | 000 | Promoted Live |  | 16 |  | 2013-08-05 10:47 |  |  |  | Document | 2013-07-15 12:29 | George Zhao/BKV/AU | 2 | 0 | 0.5 | 47200 | 49 | Steve Bartlett/BKV/AU | MQ House Keeper to show no response pricerequest.docx | 1 | 0% | MQ House Keeper to show no response pricerequest | Item | sites/BKV2/process/Change Requests
Ulrich Jensen/BKV/AU | George Zhao/BKV/AU;#206 |  | 1 | Promoted Live |  |  |  | 2014-04-30 15:12 |  |  |  | Document | 2013-10-29 10:33 | Ulrich Jensen/BKV/AU |  | 0 |  | 79872 | 64 | Josh Titley/BKV/AU | MQ Manager to include all 4.doc | 2 |  | MQ Manager to include #4 | Item | sites/BKV2/process/Change Requests
David Hoschke/BKV/AU | George Zhao/BKV/AU;#206 | 4110800% | INC000001813071 | Promoted Live |  |  |  | 2013-03-27 11:31 |  |  |  | Document | 2012-07-17 16:40 | Kamrul Zaman/BKV/AU | 2 | 0 |  | 52224 | 4 | Steve Bartlett/BKV/AU | MQ warehousing.doc |  |  | MQ warehousing | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000003012548 | Promoted Live |  | 16 |  | 2014-10-20 12:03 |  |  |  | Document | 2014-10-07 15:19 | George Zhao/BKV/AU | 0 | 0 |  | 32078 | 157 | George Zhao/BKV/AU | multiple carton order could not be started.docx | 1 |  | multiple carton order could not be started | Item | sites/BKV2/process/Change Requests
Steve Bartlett/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | INC000001708143 | Promoted Live |  |  |  | 2012-05-28 11:24 |  |  |  | Document | 2012-05-28 11:06 | Steve Bartlett/BKV/AU |  | 0 |  | 49664 | 2 | Steve Bartlett/BKV/AU | New ASLF report.doc |  |  | New ASLF report update | Item | sites/BKV2/process/Change Requests
Jun Li/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002403911 | In Progress |  |  | 2 | 2013-12-18 14:52 |  |  |  | Document | 2013-12-18 14:49 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 49664 | 99 | Ulrich Jensen/BKV/AU | New menu option for BSB file.doc | 2 |  | New menu option for BSB file | Item | sites/BKV2/process/Change Requests
Susanne Groves/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002412670 | Cancelled |  |  |  | 2014-11-27 14:53 |  |  | Cancelled as per IT demand review on 27/11/2014 | Document | 2013-10-11 16:28 | Ulrich Jensen/BKV/AU |  | 0 |  | 53248 | 60 | Josh Titley/BKV/AU | New Order source code.doc | 2 |  | New Order source code | Item | sites/BKV2/process/Change Requests
Adrian Diebold/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4123900% | INC000001981324 | Promoted Live |  |  |  | 2012-11-27 09:30 |  |  |  | Document | 2012-11-22 09:35 | Steve Bartlett/BKV/AU |  | 0 |  | 97792 | 16 | Steve Bartlett/BKV/AU | New report Non-closed Manufacturing orders.doc |  |  | New report Non-closed Manufacturing orders | Item | sites/BKV2/process/Change Requests
Carly Coleman-Price/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002347708 | In Progress |  |  |  | 2013-12-18 15:13 |  |  |  | Document | 2013-12-18 14:54 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 50176 | 100 | Ulrich Jensen/BKV/AU | No delivery fee for Credits ONLY.doc | 2 |  | No delivery fee for Credits ONLY | Item | sites/BKV2/process/Change Requests
Stephen Freestone/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000001727205 | In Progress |  |  |  | 2013-12-04 15:45 |  |  |  | Document | 2013-12-04 15:45 | Ulrich Jensen/BKV/AU |  | 0 |  | 51712 | 75 | Ulrich Jensen/BKV/AU | Non MacPac or Coda purchase reports.doc | 2 |  | Non MacPac or Coda purchase reports | Item | sites/BKV2/process/Change Requests
Istvan Kertesz/BKV/AU | George Zhao/BKV/AU;#206 | 4122846% | 11111111 | Promoted Live |  |  |  | 2012-11-15 12:02 |  |  |  | Document | 2012-11-15 11:59 | George Zhao/BKV/AU | 2 | 0 |  | 84480 | 13 | George Zhao/BKV/AU | Notification of Severity of incoming complaints and adverse reactions.doc |  |  | PO UPLOAD BUG FIX | Item | sites/BKV2/process/Change Requests
Robin Bates/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | INC000001708118 | Promoted Live |  | 16 |  | 2012-09-05 14:08 |  |  |  | Document | 2012-05-28 09:58 | Steve Bartlett/BKV/AU |  | 0 |  | 29506 | 1 | Steve Bartlett/BKV/AU | Notification of Severity of incoming complaints and adverse reactions.docx |  |  | Notification of Severity of incoming complaints and adverse reactions | Item | sites/BKV2/process/Change Requests
Prasaj Krishnan/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002357364 | In Progress |  |  |  | 2013-12-17 15:24 |  |  |  | Document | 2013-12-17 15:24 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 50688 | 88 | Ulrich Jensen/BKV/AU | Number of Orders under OLD definition.doc | 2 |  | Number of Orders under OLD definition | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002997336 | Promoted Live |  | 16 |  | 2014-10-03 11:38 |  |  |  | Document | 2014-09-23 09:59 | George Zhao/BKV/AU | 0 | 0 | 1 | 29458 | 151 | George Zhao/BKV/AU | OLA CR of NZ 11 digits mobile.docx | 1 |  | OLA CR of NZ 11 digits mobile # | Item | sites/BKV2/process/Change Requests
Susanne Groves/BKV/AU | George Zhao/BKV/AU;#206 | 4183500% | INC000001708118 | Promoted Live |  | 17 |  | 2014-07-30 14:27 |  |  | There 5 CRs related to OLA , needs a urgent change | Document | 2014-07-14 11:53 | George Zhao/BKV/AU | 0 | 0 | 1 | 34037 | 122 | Josh Titley/BKV/AU | OLA CR phone number fields.docx | 1 | 1% | OLA CR1 phone number field | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | George Zhao/BKV/AU;#206 |  | 0000 | Promoted Live |  | 16 |  | 2014-11-11 09:04 |  |  |  | Document | 2014-10-27 14:28 | George Zhao/BKV/AU | 0 | 0 | 1 | 152675 | 173 | George Zhao/BKV/AU | ola CR5 relative details deletion.docx | 2 |  | ola CR5 relative details deletion | Item | sites/BKV2/process/Change Requests
Susanne Groves/BKV/AU | George Zhao/BKV/AU;#206 |  | 0000000000000 | Promoted Live |  | 16 |  | 2014-08-08 14:40 |  |  |  | Document | 2014-08-04 10:34 | George Zhao/BKV/AU | 0 | 0 | 2 | 122845 | 128 | George Zhao/BKV/AU | Online Appointment CR2 and CR3.docx | 2 |  | Online Appointment CR2 and CR3 | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | George Zhao/BKV/AU;#206 |  | 0000 | Promoted Live |  | 16 |  | 2014-11-11 09:03 |  |  |  | Document | 2014-10-20 11:57 | George Zhao/BKV/AU | 0 | 0 |  | 1114297 | 166 | George Zhao/BKV/AU | Online Appointment CR4.docx | 2 |  | Online Appointment CR4 | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | Project | Promoted Live |  |  |  | 2014-05-30 10:15 |  |  |  | Document | 2012-06-07 09:43 | Steve Bartlett/BKV/AU | 2 | 0 |  | 71680 | 3 | Josh Titley/BKV/AU | Online History Card processing.doc | 2 |  | One line History Card processing | Item | sites/BKV2/process/Change Requests
Liliana Sanabria/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000001900930 | In Progress |  |  | 2 | 2013-12-18 13:41 |  |  |  | Document | 2013-12-18 13:41 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 25797 | 96 | Ulrich Jensen/BKV/AU | Open order with zero open quantity.docx | 2 |  | Open order with zero open quantity | Item | sites/BKV2/process/Change Requests
Carly Coleman-Price/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002511173 | Promoted Live |  | 16 |  | 2014-07-30 14:28 |  |  | Wating Istvan finish change request document | Document | 2013-11-29 15:09 | Ulrich Jensen/BKV/AU |  | 0 | 2 | 123904 | 72 | Josh Titley/BKV/AU | Opportunity pack opt IN-OUT.doc | 2 | 1% | Opportunity pack opt IN/OUT | Item | sites/BKV2/process/Change Requests
Ulrich Jensen/BKV/AU | George Zhao/BKV/AU;#206 | 4178700% | 0000 | Promoted Live |  | 16 |  | 2014-05-29 16:31 |  |  |  | Document | 2014-05-27 13:42 | George Zhao/BKV/AU |  | 0 | 1 | 29226 | 108 | George Zhao/BKV/AU | ozadapter bonus point fix.docx | 2 |  | ozadapter bonus point fix | Item | sites/BKV2/process/Change Requests
Istvan Kertesz/BKV/AU | George Zhao/BKV/AU;#206 | 4137500% | INC000002158749 | Promoted Live |  | 16 |  | 2013-04-17 14:59 |  |  |  | Document | 2013-04-11 09:51 | George Zhao/BKV/AU |  | 0 |  | 28827 | 35 | Josh Titley/BKV/AU | Past due demands report shows short incorrectly.docx | 2 |  | Past due demands report shows short incorrectly | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000001703130 | Analysis/Development |  |  |  | 2013-09-18 09:25 |  |  |  | Document | 2013-09-17 14:46 | Ulrich Jensen/BKV/AU |  | 0 |  | 139264 | 57 | Josh Titley/BKV/AU | PC Club information to WebE.doc | 2 | 100% | PC Club information to WebE | Item | sites/BKV2/process/Change Requests
Liling Wang/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002920390 | Promoted Live |  | 16 |  | 2014-09-09 09:29 |  |  | waiting request fill in the change request template | Document | 2014-09-02 09:17 | George Zhao/BKV/AU |  | 0 |  | 501503 | 138 | George Zhao/BKV/AU | PCCost report.docx | 2 |  | PCCost Report | Item | sites/BKV2/process/Change Requests
Victoria Anderson/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | INC000001993677 | Cancelled |  |  |  | 2013-03-18 11:21 |  |  |  | Document | 2013-03-05 13:39 | Steve Bartlett/BKV/AU | 2 | 0 |  | 85504 | 25 | Steve Bartlett/BKV/AU | PDC pin reset email.doc |  |  | email re-set PDC pin | Item | sites/BKV2/process/Change Requests
Sarah Begg/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4154700% | INC000002410615 | Promoted Live |  | 16 |  | 2013-10-03 14:35 |  |  |  | Document | 2013-09-25 14:30 | Steve Bartlett/BKV/AU | 2 | 0 | 1 | 52736 | 58 | Steve Bartlett/BKV/AU | Photo upload website.doc | 3 |  | Photo upload website | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | 123456 | Promoted Live |  |  |  | 2014-04-30 15:10 |  |  |  | Document | 2013-12-12 16:50 | Kyle Wilkinson/BKV/AU | 0 | 0 |  | 25356 | 80 | Josh Titley/BKV/AU | Pick Data Enquiry Option 010 in SICS menu, Husky verification.docx | 2 |  | Pick Data Enquiry Option 010 in SIBS menu | Item | sites/BKV2/process/Change Requests
Kyle Wilkinson/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | 123456 | Promoted Live |  |  |  | 2014-04-30 15:14 |  |  |  | Document | 2013-12-20 15:14 | Kyle Wilkinson/BKV/AU | 6 | 0 |  | 25540 | 102 | Josh Titley/BKV/AU | Pick Data Enquiry Option 010 in SICS menu_version 2, Husky verification.docx | 2 |  | Pick Data Enquiry Option 010 in SIBS menu | Item | sites/BKV2/process/Change Requests
Istvan Kertesz/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000002085701 | Promoted Live |  |  | 2 | 2014-10-07 14:33 |  |  |  | Document | 2013-12-17 10:14 | Ulrich Jensen/BKV/AU | 2 | 0 |  | 53760 | 85 | David Hoschke/BKV/AU | POO and Terms information in the Quote file.doc | 2 |  | POO and Terms information in the Quote file | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | George Zhao/BKV/AU;#206 | 4133300% | INC000002107165 | Promoted Live |  | 16 |  | 2013-03-05 12:23 |  |  |  | Document | 2013-02-26 14:48 | George Zhao/BKV/AU | 2 | 0 |  | 52224 | 22 | Steve Bartlett/BKV/AU | PostCode Updat in e-SalesSuite.doc |  |  | e-Salesuite Postcode Update | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4119900% | INC000001924900 | Promoted Live |  | 16 |  | 2012-11-06 14:06 |  |  |  | Document | 2012-10-16 14:39 | Steve Bartlett/BKV/AU |  | 0 |  | 51712 | 9 | Steve Bartlett/BKV/AU | QSLs not receiving HTML emails.doc |  |  | QSLs not receiving HTML emails | Item | sites/BKV2/process/Change Requests
Peter McCulloch/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002792261 | Promoted Live |  | 16 |  | 2014-09-23 10:17 |  |  |  | Document | 2014-08-26 16:10 | George Zhao/BKV/AU | 0 | 0 |  | 31723 | 136 | George Zhao/BKV/AU | Quantity Error Report not showing data.docx | 2 |  | Quantity Error Report not showing data | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4122700% | INC000001924799 | Promoted Live |  | 16 |  | 2012-11-19 10:04 |  |  |  | Document | 2012-11-13 16:25 | Steve Bartlett/BKV/AU | 2 | 0 |  | 55296 | 12 | Steve Bartlett/BKV/AU | Ranking by Year Title Change.doc |  |  | Ranking by Year Title Change | Item | sites/BKV2/process/Change Requests
Adrian Diebold/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000002235668 | In Progress |  |  | 2 | 2013-12-17 16:05 |  |  |  | Document | 2013-12-17 16:00 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 50176 | 92 | Ulrich Jensen/BKV/AU | Receipt Correction Report.doc | 2 |  | Receipt Correction Report | Item | sites/BKV2/process/Change Requests
Michelle Johnston/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC | Promoted Live |  | 16 |  | 2014-07-03 10:55 |  |  |  | Document | 2014-06-30 14:15 | Giggs Liang/BKV/AU |  | 0 | 2 | 118713 | 113 | Giggs Liang/BKV/AU | Refund -Delivery Fee Only.docx | 2 |  | Refund - Delivery Fee Only | Item | sites/BKV2/process/Change Requests
Anthony Irwin/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002277050 | Cancelled |  |  | 2 | 2014-11-27 16:47 |  |  | Cancelled as per demand review meeting on 27/11/2014 | Document | 2013-12-18 15:12 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 54272 | 101 | Josh Titley/BKV/AU | Reinstate COT report.doc | 2 |  | Reinstate COT report | Item | sites/BKV2/process/Change Requests
Gail Domenici/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000001821240 | In Progress |  |  |  | 2013-12-19 08:54 |  |  |  | Document | 2013-12-17 08:57 | Ulrich Jensen/BKV/AU | 2 | 0 |  | 49664 | 83 | Ulrich Jensen/BKV/AU | Released HELD order trail.doc | 2 |  | Released HELD order trail | Item | sites/BKV2/process/Change Requests
Katharine Aitken/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC | Promoted Live |  | 3 |  | 2014-09-22 10:22 |  |  |  | Document | 2014-09-16 14:06 | Giggs Liang/BKV/AU | 2 | 0 | 2 | 30231 | 150 | Giggs Liang/BKV/AU | Remove blacklist rep to specific account.docx | 2 |  | Fix blacklist issue and centralization | Item | sites/BKV2/process/Change Requests
Anna Stark/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4136700% | TBA | Promoted Live |  |  |  | 2013-04-03 11:42 |  |  |  | Document | 2013-04-03 08:55 | Steve Bartlett/BKV/AU |  | 0 |  | 52224 | 31 | Steve Bartlett/BKV/AU | Remove limits on competition text.doc | 2 |  | Remove limits on competition text | Item | sites/BKV2/process/Change Requests
Ricardo Castillo/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000001749949 | Cancelled |  |  | 2 | 2013-12-17 12:44 |  |  |  | Document | 2013-12-09 16:01 | Ulrich Jensen/BKV/AU |  | 0 |  | 50176 | 76 | Ulrich Jensen/BKV/AU | Report ASKPIPRA to be checked.doc | 2 |  | Report ASKPIPRA to be checked | Item | sites/BKV2/process/Change Requests
Anthony Irwin/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002268754 | In Progress |  |  | 2 | 2014-08-04 09:47 |  |  | Requirements now completed. | Document | 2013-12-17 16:16 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 56832 | 94 | Anthony Irwin/BKV/AU | Reports to folder instead of to printer.doc | 2 |  | Reports to folder instead of to printer | Item | sites/BKV2/process/Change Requests
Stephen Freestone/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000001694034 | Promoted Live | 2 |  |  | 2014-10-07 14:26 |  |  |  | Document | 2013-04-09 11:17 | David Hoschke/BKV/AU | 0 | 0 |  | 52736 | 34 | David Hoschke/BKV/AU | Request for DIFOT Tracking and Reporting Functionality.doc | 3 |  | Request for DIFOT Tracking | Item | sites/BKV2/process/Change Requests
Stephen Freestone/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000001694034 | Cancelled |  |  |  | 2014-10-07 14:28 |  |  |  | Document | 2013-06-03 15:15 | Stephen Freestone/BKV/AU | 2 | 0 |  | 56832 | 41 | David Hoschke/BKV/AU | Request for DIFOT Tracking and Reporting Functionality_Response.doc | 3 |  | Request for DIFOT Tracking | Item | sites/BKV2/process/Change Requests
Victoria Anderson/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002908594 | Promoted Live |  | 16 |  | 2014-09-15 13:59 |  |  |  | Document | 2014-08-26 12:51 | George Zhao/BKV/AU | 0 | 0 |  | 43954 | 134 | George Zhao/BKV/AU | requests for literature mail outs.docx | 2 |  | requests for literature mail outs | Item | sites/BKV2/process/Change Requests
Rod Hovell/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002308314 | Cancelled |  | 16 |  | 2014-06-27 09:51 |  |  | Cancelled due to business substantially changing requirements and owner. Asked business to re-raise a ticket so we can re-do requirements. | Document | 2013-08-28 14:30 | George Zhao/BKV/AU | 2 | 0 | 3 | 97332 | 52 | Josh Titley/BKV/AU | returns goods.docx | 2 |  | returns goods | Item | sites/BKV2/process/Change Requests
Shelley Warrington/BKV/AU | George Zhao/BKV/AU;#206 |  | 00000 | In Progress |  | 16 |  | 2014-11-25 16:47 |  |  |  | Document | 2014-11-25 12:52 | George Zhao/BKV/AU |  | 0 |  | 94813 | 187 | George Zhao/BKV/AU | Revisions to Sales Leadership Reports.docx | 2 |  | CR for Sales Leadership reports | Item | sites/BKV2/process/Change Requests
Rebecca Pearce/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000002444940 | Promoted Live |  |  | 2 | 2014-10-07 14:29 |  |  |  | Document | 2013-10-16 14:12 | Ulrich Jensen/BKV/AU | 2 | 0 |  | 25414 | 63 | David Hoschke/BKV/AU | Sales Event invites to handle more than 3 venues.docx | 2 |  | Sales Event invites to handle more than 3 venues | Item | sites/BKV2/process/Change Requests
Khaled Alali/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000002145152 | In Progress |  |  | 2 | 2013-12-17 15:44 |  |  |  | Document | 2013-12-17 15:41 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 50176 | 90 | Ulrich Jensen/BKV/AU | Sea ship mode for orders in MacPac.doc | 2 |  | Sea ship mode for orders in MacPac | Item | sites/BKV2/process/Change Requests
Tony Aguib/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | 00000000000000 | Promoted Live |  |  |  | 2013-01-31 08:51 |  |  |  | Document | 2012-12-10 10:10 | Steve Bartlett/BKV/AU | 2 | 0 |  | 319488 | 19 | Steve Bartlett/BKV/AU | Send email Notification of a mailout.doc |  |  | Send email Notification of a mailout | Item | sites/BKV2/process/Change Requests
Shane Dos Ramos | George Zhao/BKV/AU;#206 |  | INC000002823970 | Promoted Live |  | 16 |  | 2014-08-04 10:31 |  |  | George emailed Shane twice with no response. Josh advised final reminder and then cancel request. | Document | 2014-07-11 10:54 | Josh Titley/BKV/AU | 2 | 0 |  | 37408 | 119 | George Zhao/BKV/AU | SICS - Change Replenishment Cards.docx | 2 |  | Notification of Severity of incoming complaints and adverse reactions | Item | sites/BKV2/process/Change Requests
Rod Hovell/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002654262 | Cancelled |  |  |  | 2014-07-22 10:31 |  |  | CR Needs to be filled out | Document | 2014-07-11 11:07 | Josh Titley/BKV/AU | 2 | 0 |  | 28719 | 120 | George Zhao/BKV/AU | SICS - Menu 110 J5 Changes.docx | 2 |  | Notification of Severity of incoming complaints and adverse reactions | Item | sites/BKV2/process/Change Requests
Daisy Dai | George Zhao/BKV/AU;#206 |  | INC000002982560 | Promoted Live |  | 16 |  | 2014-09-17 10:32 |  |  |  | Document | 2014-09-15 11:12 | George Zhao/BKV/AU | 0 | 0 |  | 201593 | 147 | George Zhao/BKV/AU | SICS change a format of station list under option 136.docx | 1 |  | SICS change a format of station list under option 136 | Item | sites/BKV2/process/Change Requests
Rod Hovell/BKV/AU | Steve Bartlett/BKV/AU;#48 | 4136900% | INC000002132246 | Promoted Live |  |  |  | 2013-05-08 09:04 |  |  |  | Document | 2013-03-25 11:02 | Steve Bartlett/BKV/AU | 2 | 0 |  | 51712 | 28 | Steve Bartlett/BKV/AU | SICS inventory incorrect after a Maintainance.doc | 2 |  | SICS inventory incorrect after a Maintainance | Item | sites/BKV2/process/Change Requests
Rod Hovell/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC000003041353 | In Progress |  |  |  | 2014-10-24 16:38 |  |  |  | Document | 2014-10-22 14:15 | Giggs Liang/BKV/AU | 2 | 0 |  | 28192 | 170 | Giggs Liang/BKV/AU | Sics Menu Option 136.docx | 2 |  | Sics Menu Option 136 | Item | sites/BKV2/process/Change Requests
Rod Hovell/BKV/AU | Giggs Liang/BKV/AU;#554 |  | INC000002195101 | UAT |  | 4 |  | 2014-11-19 09:48 |  |  |  | Document | 2013-05-09 13:59 | Steve Bartlett/BKV/AU | 2 | 0 | 3 | 87552 | 38 | Giggs Liang/BKV/AU | SICS stock replenishment sheets.doc | 2 | 0% | SICS stock replenishment sheets | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | George Zhao/BKV/AU;#206 |  | 000000 | Promoted Live |  | 16 |  | 2014-09-26 14:26 |  |  |  | Document | 2014-09-15 09:51 | George Zhao/BKV/AU | 0 | 0 | 1 | 291800 | 145 | George Zhao/BKV/AU | signature change in acc statement and welcome email.docx | 1 |  | signature change in acc statement and welcome email | Item | sites/BKV2/process/Change Requests
Heather Cashman/BKV/AU | George Zhao/BKV/AU;#206 | 4185100% | INC000002898342 | Promoted Live |  | 16 |  | 2014-08-05 12:56 |  |  |  | Document | 2014-07-30 16:34 | George Zhao/BKV/AU |  | 0 | 1 | 28854 | 126 | George Zhao/BKV/AU | signature change of account statement.docx | 2 | 1% | signature change of account statement | Item | sites/BKV2/process/Change Requests
Victoria Anderson/BKV/AU | Hans Logeman/BKV/AU;#399 |  | INC000002094854 | In Progress |  |  | 3 | 2013-12-17 10:20 |  |  |  | Document | 2013-12-17 10:19 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 50176 | 86 | Ulrich Jensen/BKV/AU | SMS to new Representatives who order starter packs.doc | 2 |  | SMS to new Representatives who order starter packs | Item | sites/BKV2/process/Change Requests
Jeanette Yap/BKV/AU | George Zhao/BKV/AU;#206 |  | 00000 | Promoted Live |  | 16 |  | 2014-10-20 12:04 |  |  |  | Document | 2014-10-13 10:56 | George Zhao/BKV/AU | 0 | 0 |  | 29333 | 162 | George Zhao/BKV/AU | Stefania Dzurillova.docx | 2 |  | Stefania Dzurillova’s Signature v1 | Item | sites/BKV2/process/Change Requests
Stephen McCormack/BKV/AU | George Zhao/BKV/AU;#206 |  | INC000002992232 | In Progress |  |  | 16 | 2014-11-11 11:48 |  |  |  | Document | 2014-11-11 11:48 | George Zhao/BKV/AU | 0 | 0 |  | 28143 | 182 | George Zhao/BKV/AU | stop aslf report sent to redmap.docx | 2 |  | stop aslf report sent to redmap | Item | sites/BKV2/process/Change Requests
Josh Titley/BKV/AU | Giggs Liang/BKV/AU;#554 |  | N/A | Promoted Live |  | 16 |  | 2014-10-27 10:10 |  |  |  | Document | 2014-10-17 10:44 | Giggs Liang/BKV/AU | 5 | 0 |  | 632621 | 164 | Giggs Liang/BKV/AU | Stop unsupported promotion orders.docx | 2 |  | Stop unsupported promotion orders | Item | sites/BKV2/process/Change Requests
Jun Li/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000002205379 | Promoted Live |  |  | 2 | 2014-10-07 14:34 |  |  |  | Document | 2013-12-17 15:51 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 53248 | 91 | David Hoschke/BKV/AU | Summary of historical inventory movements.doc | 2 |  | Summary of historical inventory movements | Item | sites/BKV2/process/Change Requests
Cecile Janet/BKV/AU | George Zhao/BKV/AU;#206 |  | REQ000000044131 | Promoted Live |  | 16 |  | 2014-08-08 14:41 |  |  |  | Document | 2014-07-23 10:18 | George Zhao/BKV/AU | 0 | 0 | 2 | 137937 | 125 | George Zhao/BKV/AU | supply chain po CR.docx | 2 |  | Supply chain PO CR | Item | sites/BKV2/process/Change Requests
Robin Bates/BKV/AU | Steve Bartlett/BKV/AU;#48 |  | INC000001708118 | Cancelled |  |  |  | 2014-10-22 11:26 |  |  |  | Document | 2014-10-07 16:24 | George Zhao/BKV/AU | 0 | 0 |  | 28428 | 158 | Josh Titley/BKV/AU | test.docx | 2 |  | test | Item | sites/BKV2/process/Change Requests
Jennifer Hulme/BKV/AU | Stephen McCormack/BKV/AU;#18 |  | INC000001708118 | Cancelled |  |  |  | 2014-10-07 14:27 |  |  |  | Document | 2013-09-16 14:26 | Jennifer Hulme/BKV/AU | 2 | 0 | 5 | 53248 | 56 | David Hoschke/BKV/AU | Test2.doc | 3 | 90% | Test2 | Item | sites/BKV2/process/Change Requests
Tony Aguib/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | TPP | Promoted Live |  |  |  | 2014-10-07 14:29 |  |  |  | Document | 2013-11-05 14:46 | Ulrich Jensen/BKV/AU |  | 0 |  | 53760 | 66 | David Hoschke/BKV/AU | Traffic light in CS order creation.doc | 2 | 100% | Traffic light in CS order creation | Item | sites/BKV2/process/Change Requests
Cecile Janet/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC000002575613 | In Progress |  |  |  | 2014-01-15 14:51 |  |  |  | Document | 2014-01-15 14:51 | Ulrich Jensen/BKV/AU |  | 0 |  | 50176 | 105 | Ulrich Jensen/BKV/AU | Update POs automatically when change of ETD.doc | 2 |  | Update POs automatically when change of ETD | Item | sites/BKV2/process/Change Requests
Rod Hovell/BKV/AU | Ulrich Jensen/BKV/AU;#16 |  | INC000001755152 | In Progress |  |  |  | 2013-12-09 16:11 |  |  |  | Document | 2013-12-09 16:09 | Ulrich Jensen/BKV/AU | 0 | 0 |  | 50176 | 77 | Ulrich Jensen/BKV/AU | Web based report for Macpac option 61 3and4.doc | 2 |  | Web based report for Macpac option 61 3&4 | Item | sites/BKV2/process/Change Requests
Istvan Kertesz/BKV/AU | David Hoschke/BKV/AU;#170 |  | INC00003074832 | Analysis/Development | 5 |  |  | 2014-11-13 19:58 |  |  |  | Document | 2014-11-06 15:06 | David Hoschke/BKV/AU | 0 | 0 |  | 61976 | 180 | Istvan Kertesz/BKV/AU | X15 - Representative Profit details.docx | 2 |  | X15 - Representative Profit details | Item | sites/BKV2/process/Change Requests