## Flow(Landscape)
| Transition Planning | Knowledge Transfer | Secondary Support | Primary Support
AVON Responsibility | •Re-verification of the list of all applications to be included in the cluster •Identification of appropriate SME’s for KT/SS/PS and confirm availability •Prioritization of applications within the cluster by criticality and size •Discuss by application: •The key components and important support activities •Level of customization •Governance: Introduction to Managed Services | •Availability for KT sessions •Application Overview •Business •Technical •Functional •Application walkthrough •Discussion on application interfaces •Database details •Code walk through of critical components •Support Overview •Support Activities •Typical tickets •Open tickets •Application Environments & Installation •Weekly Q&A •Attend reverse presentations •Reverse KT evaluation •Application Information Document Review | •Review of code changes / fixes, impact analysis done by ISS •Clarification of additional questions and issues for ISS •Joint walkthrough of complex code changes and bug-fixes done by Avon •Governance: Service Level Agreements •GSC/Remedy updates •System Access | •Review of complex or critical code changes / fixes, impact analysis done by vendor •Assist vendor team in resolving incidents and requests, if required by vendor •Governance: Meetings and Reporting
ISS RESPONSIBILITY | •ISS internal training for AVON business •Classify the applications by Application Programming Language •Assign proper staffs to takeup different applications •Identification of necessary information for KT | •Assignation of appropriate staff to participate KT sessions •Collection of Documents (refer to System level check list) •Summarize necessary supporting knowledge(refer to check list) •KT evaluation •Preparation of reverse presentation | •Resolving incidents and requests with AVON team •Raise additional questions and issues to SME if any •Collect information of code changes and bug-fixes •Provide details of code changes/fixes, impact analysis to AVON team | •Resolve incidents and requests •Acquire advices from SME for criticall incidents and mark down appropriate solution
OUTPUT | •Develop and generate document of basic concept for AVON business •Transition Flow •Applications - Staffs mapping •Transition team contact list •KT check list | •Completed KT check list •Build up system information data base •Generate support guide for different systems (Cover: 1.functional knowledge 2.operational knowledge 3.Application technical environment 4.Incident handling procedure) •Accomplished reverse presentations | •Fulfil Service Level Agreements •Improve the quality of system information database on ISS site •Improve the quality of support guide on ISS site | •Fulfil Service Level Agreements •Improve the quality of system information database on ISS site •Improve the quality of support guide on ISS site

## Procedure level check list
General working information | Item | Details | Provide by | Status
Contact Point (Name/Post/Phone/mailing address/mailing group) | User Contact point | NA | Local IT
| Related support contact point | Up/Down Stream System | Local IT
|  | IT Operation Team(Includes Network/Server/Security Admin/etc) | Local IT
Working process | Incident handling standard | Includes: 1.Problem reporting standard(email/incident tickets) 2.Priority identification standard 3.System Authority control 4.Data patching standard flow 5.Program changes standard flow 6.Emergency treatment options and processing steps of Critical functions 7.Daily operation maintenances' procedure | Local IT/ISS summarize
Knowledge Base | Issue handling tips | Includes: 1.Repeated issue handling tips 2.High piority issue handling log 3.Tools for current supporting 4.Mail history for previous issue handling. 5.Issue handling log(program change log/data patching log) 6.Drill related document | Local IT/ISS summarize

## System Level check list
System information
Region | Technical base | System Name | Items | Details | Provide by | Status
ANZ | AS400 | Actionware | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4. Data transfer between up/down stream system 5.Emergency treatment options and processing steps of Critical functions 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any)\ | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  | Macpac | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4. Data transfer between up/down stream system 5.Emergency treatment options and processing steps of Critical functions 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any)\ | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  | RB3 | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4. Data transfer between up/down stream system 5.Emergency treatment options and processing steps of Critical functions 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any)\ | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  | BlueFax |  |  | Local IT
|  | Halcyon |  |  | Local IT
|  | Aldon |  |  | Local IT
| C#/VB.NET/VB6 | SICS | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4. Data transfer between up/down stream system 5. Interfaces details 6. Batch jobs details. 7. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any)\ | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment | Local IT
|  | OLA | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4. Data transfer between up/down stream system 5. Interfaces details 6. Batch jobs details. 7. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any)\ | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment | Local IT
China | C#/VB.NET/VB6/ASP/PLSQL | DRMSP | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
| C#/VB.NET/VB6/ASP/PLSQL | CIA | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
| C#/VB.NET/VB6/ASP/PLSQL | ADCP | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
| C#/VB.NET/VB6/ASP/PLSQL | KPI | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
| AXAPTA/C#/VB.NET/PLSQL | AXAPTA | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
Taiwan | C#/VB.NET/VB6/ASP/PLSQL | DRMPOS | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
| C#/VB.NET/VB6/ASP/PLSQL | DRMARMS | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
| C#/VB.NET/VB6/ASP/PLSQL | DMS | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
| C#/VB.NET/VB6/ASP/PLSQL | CIA | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
| AXAPTA/C#/VB.NET/PLSQL | AXAPTA | System Overview | 1. System Architecture 2. Data flow/Business cycle 3. Details of different modules(PGM flow/Critical files for the module) 4.Emergency treatment options and processing steps of Critical functions 5. Data transfer between up/down stream system 6. Interfaces details 7. Batch jobs details. 8. Data backup/sync with backup machine | Local IT
|  |  | System enhancement related documents | 1.User requirement 2.Amendment spec 3.Functional spec 4.Program design 5.Testing 6.release details(especially Incidents related to the enhancement) | Local IT
|  |  | Documents for bussiness knowledge | 1.User guide 2.Functional Spec | Local IT
|  |  | Production environment | 1.Server information 2.Production library list 3.Production program sources 4.Support tools(if any) 5.Production environment(SBS/JOBQ/JOBD/etc) 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT
|  |  | Backup environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) | Local IT
|  |  | Testing environment | 1.Server information 2.Library list 3.Program sources 4.Support tools(if any) 5.Environment 6.Application access/Avon account and Remedy system access/Database access/Sourcesafe access | Local IT

## Initial Access(ANZ)
Technical base | System | Items | Access Tools | Permission | Status
General | General | Email | Outlook | Email account | Waiting
|  | Remedy |  | Read/Write/Modify | Waiting
|  | VPN | VPN | VPN access account | Waiting
| Actionware | iaccess for windows | NA | Please kindly provide the installation package with appropriate version. If the installation package is not availabl, Please kindly suggest acceptable alternative(eg . Mocha TN5250) | Waiting
|  | Prod Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for production environment 3. Application login | Waiting
|  | Backup Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for backup environment 3. Application login | Waiting
|  | Testing Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for testing environment 3. Application login | Waiting
|  | Authority setup details | Please attach reports here | Please kindly provide the full authority setup reports about the login profiles to PROD/BACKUP/Testing server, Reports should include: 1. Objects (LIB/PF/PGM/SBSD/JOBD/etc) 2. Commands | Waiting
| Macpac | Remedy |  | Read/Write/Modify | Waiting
|  | Email | Outlook | Email account | Waiting
|  | VPN | VPN | VPN access account | Waiting
|  | iaccess for windows | NA | Please kindly provide the installation package with appropriate version. If the installation package is not availabl, Please kindly suggest acceptable alternative(eg . Mocha TN5250) | Waiting
|  | Prod Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for production environment 3. Application login | Waiting
|  | Backup Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for backup environment 3. Application login | Waiting
|  | Testing Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for testing environment 3. Application login | Waiting
|  | Authority setup details | Please attach reports here | Please kindly provide the full authority setup reports about the login profiles to PROD/BACKUP/Testing server, Reports should include: 1. Objects (LIB/PF/PGM/SBSD/JOBD/etc) 2. Commands | Waiting
| RB3 | VPN | VPN | VPN access account | Waiting
|  | iaccess for windows | NA | Please kindly provide the installation package with appropriate version. If the installation package is not availabl, Please kindly suggest acceptable alternative(eg . Mocha TN5250) | Waiting
|  | Prod Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for production environment 3. Application login | Waiting
|  | Backup Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for backup environment 3. Application login | Waiting
|  | Testing Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for testing environment 3. Application login | Waiting
|  | Authority setup details | Please attach reports here | Please kindly provide the full authority setup reports about the login profiles to PROD/BACKUP/Testing server, Reports should include: 1. Objects (LIB/PF/PGM/SBSD/JOBD/etc) 2. Commands | Waiting
| BlueFax/ Halcyon/ Aldon/ Gumbo/ Other AS400 related system | iaccess for windows | NA | Please kindly provide the installation package with appropriate version. If the installation package is not availabl, Please kindly suggest acceptable alternative(eg . Mocha TN5250) | Waiting
|  | Prod Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for production environment 3. Application login | Waiting
|  | Backup Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for backup environment 3. Application login | Waiting
|  | Testing Server | iaccess for windows | 1.IP/DNS 2.Server level profiles for testing environment 3. Application login | Waiting
|  | Authority setup details | Please attach reports here | Please kindly provide the full authority setup reports about the login profiles to PROD/BACKUP/Testing server, Reports should include: 1. Objects (LIB/PF/PGM/SBSD/JOBD/etc) 2. Commands | Waiting
| OLA | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
| SICS | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting

## Initial access(CN & TW)
Region | System | Items | Access Tools | Permission | Status
General | General | Email | Outlook | Email account | Waiting
|  | Remedy |  | Read/Write/Modify | Waiting
|  | VPN | VPN | VPN access account | Waiting
China | DRMSP | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
| CIA | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
| ADCP | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
| KPI | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
| AXAPTA | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
Taiwan | DRMPOS | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | Application Compile Server(Test) for Java/WindowXP |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
| DRMARMS | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
| DMS | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
| CIA | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting
| AXAPTA | Database(Product) | Oracle client/Toad | Read | Waiting
|  | Database(Test) | Oracle client/Toad | Read/Write/Modify/Run | Waiting
|  | Domain(Product) | Terminal | Remote logon | Waiting
|  | Domain(Test) | Terminal | Remote logon | Waiting
|  | Application Server(Product) |  | Read | Waiting
|  | Application Server(Test) |  | Read/Write/Modify/Run | Waiting
|  | SourceCode(Product) | SourceSafe | Read | Waiting
|  | SourceCode(Test) | SourceSafe | Read/Write/Modify | Waiting
|  | Interface file server(Product) |  | Read | Waiting
|  | Interface file server(Test) |  | Read/Write/Modify | Waiting
|  | System & Application log file(Product) |  | Read | Waiting
|  | System & Application log file(Test) |  | Read/Write/Modify | Waiting

## Transition plan .NET(ANZ) Opt1
|  | Week1 2nd Feb - 6th Feb | Week2 9th Feb - 13th Feb | Week3 16th Feb - 20th Feb | Week4 23th Feb - 27th Feb
Mon | AM | •Application specific Development Process KT •Release Management Process •Infrastructure Support Specific process KT •Infrastructure Inventory & Metrics •ISS present agreed Incident/CR process flow and acknowledge SME responsibility | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Perform SICS reverse KT on PM | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Work with
| PM | •Review, Summarize & File Development process •Review, Summarize & File Release Management process •Review, Summarize & File infrastructure Support Specific process •Preparation for KT Mainly focus on documents study |  | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Preparation for Application detail walkthrough
Tue | AM | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Q&A | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Perform OLA reverse KT on PM | •Resolve historical complex incident •Attend online Remedy Training
| PM | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Preparation for Application detail walkthrough | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Preparation for Application detail walkthrough
Wed | AM | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down | •Resolve historical complex incident •Attend online Remedy Training
| PM | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query
Thu | AM | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down | •Verify summerized and updated documents •Work with SME to solve unclear queries •Prepare reverse presentation •Attend online Remedy Training
| PM | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query
Fri | AM | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Reverse presentation •Reverse presentation Incident handling procedure All systems' supporting overview Ongoing target
| PM | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure | •Help summarize and update current documents about: Business Process Design & Architecture Implementation
|  | VB.NET/C#/VB6 | SICS
OLA

## Transition plan AS400(ANZ) Opt1
|  | Week1 2nd Feb - 6th Feb | Week2 9th Feb - 13th Feb | Week3 16th Feb - 20th Feb | Week4 23th Feb - 27th Feb
Mon | AM | •Application specific Development Process KT •Release Management Process •Infrastructure Support Specific process KT •Infrastructure Inventory & Metrics •ISS present agreed Incident/CR process flow and acknowledge SME responsibility | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Preparation for Actionware KT •Perform RB3 reverse KT in PM | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details
| PM | •Double check listed necessary documents •Preparation for KT Mainly focus on documents study |  | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Preparation for Application detail walkthrough | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query
Tue | AM | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT
| PM | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Preparation for Application detail walkthrough | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Preparation for Application detail walkthrough | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure •Attend online Remedy Training
Wed | AM | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Perform reverse KT in PM •Attend online Remedy Training
| PM |  | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure
Thu | AM | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Preparation for other AS400 related applications KT •Perform MACPAC reverse KT in PM | •Review summerized and updated documents •Work with SME to solve unclear queries •Prepare reverse presentation •Attend online Remedy Training
| PM |  | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure
Fri | AM | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Preparation for Macpac KT •Perform Actionware reverse KT in PM | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Reverse presentation
| PM | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure |  | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Preparation for Application detail walkthrough
Sat | AM
PM
Sun | AM
PM
|  | AS/400 (RPG & Cobol) | RB3 | *Critical
Macpac
Actionware
BlueFax/ Halcyon/ Aldon/ Gumbo

## Transition plan .NET(ANZ) Opt2
|  | Week1 2nd Feb - 6th Feb | Week2 9th Feb - 13th Feb | Week3 16th Feb - 20th Feb | Week4 23th Feb - 27th Feb | Week5 2nd Mar - 6th Mar
Mon | AM | •Application specific Development Process KT •Release Management Process •Infrastructure Support Specific process KT •Infrastructure Inventory & Metrics •ISS present agreed Incident/CR process flow and acknowledge SME responsibility | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Q&A | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Perform OLA reverse KT | •Review representational incidents for critical component
| PM | •Review, Summarize & File Development process •Review, Summarize & File Release Management process •Review, Summarize & File infrastructure Support Specific process •Preparation for KT Mainly focus on documents study | •Help AS400 team summarize and update current documents about: Business Process Design & Architecture Implementation •Review documents about SICS | •Help AS400 team summarize and update current documents about: Business Process Design & Architecture Implementation •Review documents about OLA
Tue | AM | Preparation for SICS KT •Go through application overview and write down related queries •Confirm critical component from Local SME and review its process and write down program flow •Review interfaces summary and highlight critical information(eg. Data transfer flow/RB3 process) •Draft reverse KT template base on SME KT session ppt | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Work with •Remedy training at night | •Review representational incidents for critical component
| PM |  | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Update apllication overview details in reverse KT template | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Update apllication overview details in reverse KT template
Wed | AM | Preparation for SICS KT •Go through application overview and write down related queries •Confirm critical component from Local SME and review its process and write down program flow •Review interfaces summary and highlight critical information(eg. Data transfer flow/RB3 process) •Draft reverse KT template base on SME KT session ppt | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Work with •Remedy training at night | •Review representational incidents for critical component
| PM |  | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query •Update critical component process flow details in reverse KT template •Update interfaces details in reverse KT template | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query •Update critical component process flow details in reverse KT template •Update interfaces details in reverse KT template
Thu | AM | Preparation for OLA KT •Go through application overview and write down related queries •Confirm critical component from Local SME and review its process and write down program flow •Review interfaces summary and highlight critical information(eg. Data transfer flow/RB3 process) •Draft reverse KT template base on SME KT session ppt | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Verify summerized and updated documents •Work with SME to solve unclear queries •Prepare reverse presentation
| PM |  | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure •Augement reverse KT template | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure •Augement reverse KT template | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Update apllication overview details in reverse KT template •Remedy training at night
Fri | AM | Preparation for OLA KT •Go through application overview and write down related queries •Confirm critical component from Local SME and review its process and write down program flow •Review interfaces summary and highlight critical information(eg. Data transfer flow/RB3 process) •Draft reverse KT template base on SME KT session ppt | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Perform SICS reverse KT | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down | •Reverse presentation Incident handling procedure All systems' supporting overview Ongoing target
| PM |  |  | •Help AS400 team summarize and update current documents about: Business Process Design & Architecture Implementation
|  | AS/400 (RPG & Cobol) | RB3
Macpac
Actionware
BlueFax/ Halcyon/ Aldon/ Gumbo
|  | VB.NET/C#/VB6 | SICS
OLA
Note on C2: William Feng: Add below item •ISS present agreed Incident/CR process flow and acknowledge SME responsibility
Note on C4: William Feng: prepare KT session next week
Note on D4: William Feng: 1. Due to some parts of document works were done on week1, suppose we can prepare reverse KT session after each KT session
Note on F4: William Feng: *If .Net team accomplish 80% of their task and AS400 team have problem on their document works, please provide helps to AS400 team
Note on D5: William Feng: Add below •Update apllication overview details in reverse KT template
Note on C6: William Feng: prepare KT session next week
Note on F6: William Feng: *If .Net team accomplish 80% of their task and AS400 team have problem on their document works, please provide helps to AS400 team
Note on D7: William Feng: Add below •Update critical component process flow details in reverse KT template •Update interfaces details in reverse KT template
Note on C8: William Feng: prepare KT session next week
Note on C10: William Feng: Chaged to prepare KT session next week
Note on D10: William Feng: Perform below iitem in PM •Perform SICS reverse KT

## Transition plan AS400(ANZ) Opt2
|  | Week1 2nd Feb - 6th Feb | Week2 9th Feb - 13th Feb | Week3 16th Feb - 20th Feb | Week4 23th Feb - 27th Feb | Week5 2nd Mar - 6th Mar
Mon | AM | •Application specific Development Process KT •Release Management Process •Infrastructure Support Specific process KT •Infrastructure Inventory & Metrics •ISS present agreed Incident/CR process flow and acknowledge SME responsibility | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT
| PM | •Double check listed necessary documents •Summarize and file Application specific Development Process Release Management Process Infrastructure Support Specific process | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Update apllication overview details in reverse KT template | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Update apllication overview details in reverse KT template | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query •Update critical component process flow details in reverse KT template •Update interfaces details in reverse KT template | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure •Augement reverse KT template
Tue | AM | Preparation for RB3 KT •Go through application overview and write down related queries •Confirm critical component from Local SME and review its process and write down program flow •Review interfaces summary and highlight critical information(eg. Data transfer flow/RB3 process) •Draft reverse KT template base on SME KT session ppt | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Perform reverse KT
| PM |  |  | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query •Update critical component process flow details in reverse KT template •Update interfaces details in reverse KT template | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure •Augement reverse KT template •Remedy training at night
Wed | AM | Preparation for Actionware KT •Go through application overview and write down related queries •Confirm critical component from Local SME and review its process and write down program flow •Review interfaces summary and highlight critical information(eg. Data transfer flow/Actionware process) •Draft reverse KT template base on SME KT session ppt | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query •Update critical component process flow details in reverse KT template •Update interfaces details in reverse KT template | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Perform MACPAC reverse KT •Remedy training at night | •Review representational incidents for critical component •Review summerized and updated documents •Work with SME to solve unclear queries •Prepare reverse presentation
| PM |  |  | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure •Augement reverse KT template
Thu | AM | Preparation for MACPAC KT •Go through application overview and write down related queries •Confirm critical component from Local SME and review its process and write down program flow •Review interfaces summary and highlight critical information(eg. Data transfer flow/MACPAC process) •Draft reverse KT template base on SME KT session ppt | •Support activities •Typical tickets sharing •Solution of Repeated issues •Open tickets review •DR process KT | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Preparation for Macpac KT •Perform Actionware reverse KT | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Review representational incidents for critical component •Review summerized and updated documents •Work with SME to solve unclear queries •Prepare reverse presentation
| PM |  | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure •Augement reverse KT template |  | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Update apllication overview details in reverse KT template •Remedy training at night
Fri | AM | Preparation for BlueFax/Halcyon/Aldon/Gumbo KT •Go through application overview and write down related queries •Confirm critical component from Local SME and review its process and write down program flow •Review interfaces summary and highlight critical information(eg. Data transfer flow/System process) •Draft reverse KT template base on SME KT session ppt | •Organize updated & summarize documents •Simulate & verify learned knowledge in testing environment •Queries, if any, raise to AVON SME and record down •Perform RB3 reverse KT | •Application overview •Business Process KT •Design & Architecture KT •Implementation KT •Interface overview •Q&A | •Application walkthrough •Interfaces walk through •Code walk through of critical components •Critical files(database) details | •Reverse presentation Incident handling procedure All systems' supporting overview Ongoing target
| PM |  |  | •Summarize and update current documents about: Business Process Design & Architecture Implementation •Discuss with SME for related query •Update apllication overview details in reverse KT template | •Summarize & file function and logic for critical program •Summarize & file critical database details •Summarize & file interfaces details •Discuss with SME for related query •Update critical component process flow details in reverse KT template •Update interfaces details in reverse KT template
Sat | AM
PM
Sun | AM
PM
|  | AS/400 (RPG & Cobol) | RB3 | *Critical
Macpac
Actionware
BlueFax/ Halcyon/ Aldon/ Gumbo
|  | VB.NET/C#/VB6 | SICS
OLA
Note on C2: William Feng: Add below item •ISS present agreed Incident/CR process flow and acknowledge SME responsibility
Note on D3: William Feng: Add below •Update apllication overview details in reverse KT template
Note on C4: William Feng: prepare KT session next week
Note on D6: William Feng: Add below: •Update interfaces details in reverse KT template
Note on G6: William Feng: KT Finalization, Review and ensure necessary information handover to ISS
Note on D9: William Feng: Add below: •Augment reverse KT template
Note on D10: William Feng: Perform below iitem during PM •Perform RB3 reverse KT
Note on G10: William Feng: Final representation

## Transition plan detail (China)
China Schedule |  | Week1 2nd Feb - 6th Feb | Week2 9th Feb - 13th Feb | Week3 16th Feb - 20th Feb | Week4 23th Feb - 27th Feb | Week5 2nd Mar - 6th Mar | Week6 9th Mar - 13th Mar
Mon | AM | •The overall structure and data flow between each system •Application specific Development Process KT •Release Management Process •Infrastructure Support Specific process KT •Infrastructure Inventory & Metrics | •Data backup/sync with backup machine •DR process KT •Summarize and update current documents about: Business Process Design & Architecture Implementation | •Verify summerized and updated documents •Work with SME to solve unclear queries | •Review documents & Prepare reverse presentation | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT | •Code walk through of critical components •Critical files(database) details
| PM | •Review, Summarize & File Development process •Review, Summarize & File Release Management process •Review, Summarize & File Release Support Specific process •Reverse presentation of the overall and process | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure •Q&A, update file | •Verify summerized and updated documents •Work with SME to solve unclear queries | •Review documents & Prepare reverse presentation | •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules | •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues
Tue | AM | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT | •Review current tickets •Application Environments & Installation rehearsal | •Review documents & Prepare reverse presentation | •Code walk through of critical components •Critical files(database) details | •Data backup/sync with backup machine •DR process KT •Summarize and update current documents about: Business Process Design & Architecture
| PM | •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules | •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules | •Prepare reverse presentation | •Attend online Remedy Training | •Code walk through of critical components •Critical files(database) details | •Summarize & update File procedures of critical program and regular support activities •Summarize & update file critical database details •Summarize & update file interfaces details •Summarize & update File DR information & procedure •Discuss with SME for related query •Q&A, update file
Wed | AM | •Code walk through of critical components •Critical files(database) details | •Code walk through of critical components •Critical files(database) details |  | •Review documents & Prepare reverse presentation | •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules
| PM | •Code walk through of critical components •Critical files(database) details | •Code walk through of critical components •Critical files(database) details |  | •Attend online Remedy Training | •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues | •Code walk through of critical components •Critical files(database) details •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions
Thu | AM | •Code walk through of critical components •Critical files(database) details | •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions |  | •Review documents & Prepare reverse presentation | •Data backup/sync with backup machine •DR process KT •Summarize and update current documents about: Business Process Design & Architecture | •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues •Data backup/sync with backup machine •DR process KT
| PM | •Summarize & update file function and logic for critical program •Summarize & update file critical database details •Summarize & update file interfaces details •Discuss with SME for related query | •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues |  | •Attend online Remedy Training | •Summarize & update File procedures of critical program and regular support activities •Summarize & update file critical database details •Summarize & update file interfaces details •Summarize & update File DR information & procedure •Discuss with SME for related query •Q&A, update file | •Summarize & update File procedures of critical program and regular support activities •Summarize & update file critical database details •Summarize & update file interfaces details •Summarize & update File DR information & procedure •Discuss with SME for related query •Summarize and update current documents about: Business Process Design & Architecture •Q&A, update file
Fri | AM | •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions | •Data backup/sync with backup machine •DR process KT •Summarize and update current documents about: Business Process Design & Architecture |  | •Review documents & Prepare reverse presentation | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT | •reverse presentations
| PM | •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues | •Summarize & update File procedures of critical program and regular support activities •Summarize & update file critical database details •Summarize & update file interfaces details •Summarize & update File DR information & procedure •Discuss with SME for related query •Q&A, update file |  | •Review documents & Prepare reverse presentation | •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules | •reverse presentations •Application Information Document Review & Update
Sat | AM
PM
Sun | AM
PM
General
DRMSP
CIA
KPI
ADCP
AXAPTA
Holiday

## Transition plan detail (Taiwan)
Taiwan Schedule |  | Week1 2nd Feb - 6th Feb | Week2 9th Feb - 13th Feb | Week3 16th Feb - 20th Feb | Week4 23th Feb - 27th Feb | Week5 2nd Mar - 6th Mar | Week6 9th Mar - 13th Mar
Mon | AM | •The overall structure and data flow between each system •Application specific Development Process KT •Release Management Process •Infrastructure Support Specific process KT •Infrastructure Inventory & Metrics | •Data backup/sync with backup machine •DR process KT •Summarize and update current documents about: Business Process Design & Architecture Implementation | •Verify summerized and updated documents •Work with SME to solve unclear queries | •Review documents & Prepare reverse presentation | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT | •Code walk through of critical components •Critical files(database) details
| PM | •Review, Summarize & File Development process •Review, Summarize & File Release Management process •Review, Summarize & File Release Support Specific process •Reverse presentation of the overall and process | •Summarize & File procedures of regular support activities •Summarize & File DR information & procedure •Q&A, update file | •Verify summerized and updated documents •Work with SME to solve unclear queries | •Review documents & Prepare reverse presentation | •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules | •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues
Tue | AM | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT | •Review current tickets •Application Environments & Installation rehearsal | •Review documents & Prepare reverse presentation | •Code walk through of critical components •Critical files(database) details | •Data backup/sync with backup machine •DR process KT •Summarize and update current documents about: Business Process Design & Architecture
| PM | •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules | •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules | •Prepare reverse presentation | •Attend online Remedy Training | •Code walk through of critical components •Critical files(database) details | •Summarize & update File procedures of critical program and regular support activities •Summarize & update file critical database details •Summarize & update file interfaces details •Summarize & update File DR information & procedure •Discuss with SME for related query •Q&A, update file
Wed | AM | •Code walk through of critical components •Critical files(database) details | •Code walk through of critical components •Critical files(database) details |  | •Review documents & Prepare reverse presentation | •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules
| PM | •Code walk through of critical components •Critical files(database) details | •Code walk through of critical components •Critical files(database) details |  | •Attend online Remedy Training | •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues | •Code walk through of critical components •Critical files(database) details •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions
Thu | AM | •Code walk through of critical components •Critical files(database) details | •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions |  | •Review documents & Prepare reverse presentation | •Data backup/sync with backup machine •DR process KT •Summarize and update current documents about: Business Process Design & Architecture | •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues •Data backup/sync with backup machine •DR process KT
| PM | •Summarize & update file function and logic for critical program •Summarize & update file critical database details •Summarize & update file interfaces details •Discuss with SME for related query | •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues |  | •Attend online Remedy Training | •Summarize & update File procedures of critical program and regular support activities •Summarize & update file critical database details •Summarize & update file interfaces details •Summarize & update File DR information & procedure •Discuss with SME for related query •Q&A, update file | •Summarize & update File procedures of critical program and regular support activities •Summarize & update file critical database details •Summarize & update file interfaces details •Summarize & update File DR information & procedure •Discuss with SME for related query •Summarize and update current documents about: Business Process Design & Architecture •Q&A, update file
Fri | AM | •Application Interfaces walk through •Emergency treatment options and processing steps of Critical functions | •Data backup/sync with backup machine •DR process KT •Summarize and update current documents about: Business Process Design & Architecture |  | •Review documents & Prepare reverse presentation | •Application Business/Technical/Functional Overview •User requirement and system design walkthrough •Data flow/Business cycle •Implementation KT | •reverse presentations
| PM | •Batch & Schedule jobs details •Support activities •Typical tickets sharing •Solution of Repeated issues | •Summarize & update File procedures of critical program and regular support activities •Summarize & update file critical database details •Summarize & update file interfaces details •Summarize & update File DR information & procedure •Discuss with SME for related query •Q&A, update file |  | •Review documents & Prepare reverse presentation | •Application Details of different modules(PGM flow/Critical files for the module) •Database details of different modules | •reverse presentations •Application Information Document Review & Update
Sat | AM
PM
Sun | AM
PM
General
DRMPOS
DRMARMS
CIA
DMS
AXAPTA
Holiday

## Detail Task on CR process
A: Accountable I: Inform | GWE Release Management | APAC Regional Deployment Team | Development Team | Global Admin/ Infra Team | Local IT/ Business User
Local IT/BU Raise Pre-CR - Email | A | I | I |  | I
QC Number creation in Mercury |  | A | I
QC Status Update |  | A | I
CR Review | I | I | A |  | I
Analysis Impact Discussion - AI Doc | I | I | A | I | I
Solution Mapping Discussion - SM Doc | I | I | A | I | I
CR Timeline construction | I | A | I | I | I
CR and SM Signoff | I | I |  |  | A
Development and UT Stage | I | I | A | I
UT Signoff, Install Document, Run Guide | I | I | A | I | I
Communicate with Local, Global for QA environment Preparation | A | I |  | I | I
UAT Stage, UAT Signoff | I | I |  |  | A
QC Gaps Analysis Discussion - Impact Analysis on Open CR with Dev Team | I | I | A | I
CRQ number creation from Remedy | A | I
Remedy Update, Approval Process | A | I | I | I | I
CAB Approval Process | A | I |  | I | I
Deployment Cordination on Pre-deployment w Global Admin, Infra | A | I |  | I | I
Post-Deployment Cordination - to close CR | I | I |  | A | I
Close CR | A |  |  |  | I

## Roles and Responsibility
R : Responsible C: Consult I: Inform | Development Team | Local SME Team | Local Infra Team
Business Requirement Document | I | R | I
Analysis Impact Document | I | R
Change Request Review & Discussion | I | R | I
Change Request & Test Scenario | I | R | I
Solution Mapping Document | R | C
Coding | R | C
Unit Test & Signoff | R | I
User Guide | R | I
Install Plan Doc - QA | R | C | C
QA test & Signoff | I | R
UAT & Signoff | I | R
Install Plan Doc - Production | R | C | C
Pre-Production Discussion (If Require) | C | R | C
Approval Process - Scheduling CRQ and Communication to the team | I | R | I
.NET Deployment | C | I | R
AS400 Deployment | C | R | I
Closure | I | R | I
Post-Implementation Review Doc (For Issue only) | I | R | I

## Sheet1
R : Responsible C: Consult I: Inform | Local Deployment Team | Production Support Team | Local SME Team | Infra Team
User queries |  | I | R
Incident ticket |  | I | R
Insident Review & Investigation |  | R | C
Insident Report |  | R | I
Analysis Impact Document | C | I | R
Solution Mapping Document | C | I | R
Unit Test & Signoff (If Require) | I | R | I
Run Guide (If Require) | I | R | I
Install Plan Doc - QA (If Require) | C | R | I | I
UT & Signoff (If Require) | C | C | R
Install Plan Doc - Production (If Require) | C | R | I | I
Pre-Production Discussion (If Require) | C | C | R | I
Approval Process - Scheduling CRQ and Communication to the team | C | I | R | I
Deployment (If Require) | I | C | I | R
Closure | C | I | R
Post-Implementation Review Doc (For Issue only) (If Require) | C | I | R | I

## ANZ related system
This column should have unique values | [12 empty] | Contact Information |  |  |  | Technology Components (If you don’t find values in the list please enter your own)
Application Acronym/Abbreviation | Full name | Others | Short description (255 Characters) | Description/Definition | Manufacturer | Criticality | Standardization Status | Avon Application Category | AVON Application Function (If you don’t find values in the list please enter your own,prefix with NEW_ ) | Primary Authentication Method | Avon Application Architecture Deployment Model | Avon Application License Type | IT Owner (FirstName.LastName) Primary Contact | IT Owner (Org Unit) | Business Owner (FirstName.LastName) | Business Owner (Org Unit) | Operating System | DBMS | Application Programming Language | Application Hardware Platform | IT Owner (FirstName.LastName) Secondary Contact | Application Road Map | App Service Date (mm/dd/yyyy) | App Retired Date (mm/dd/yyyy) | Vendor Support End Date (mm/dd/yyyy) | App Archival Status | App Archival Date (mm/dd/yyyy) | App Data Archival Status | App Data Archival Date (mm/dd/yyyy) | Hosting Type | External Hosting Provider Name | Application DR Plan Availability Status | Application DR Type | DR Data Replication Type | RTO (Recovery Time Objective) | RPO (Recovery Point Objective) | Last date of DR Test (mm/dd/yyyy) | DR Plan document (Sharepoint URL) | Evidence of Last DR Test (SharePoint URL)
Actionware | Actionware |  | Call Centre - Representative management | Call Centre - Representative management | APPINTECH corp | High | Specialized | Local | Sell Products - Representative Support | Application | Other | Concurrent Users | Richard.Hutchings | IT ANZ | Rachel.Kotthoff | Customer & Representative services | OS/400 | DB2/400 | RPG | IBM AS/400 | None | Maintain | 1996-09-30 |  |  | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous | 48 to 60 hrs |  | 2012-09-21 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F8 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F9
Coda | Coda |  | Financil G/L | Financil G/L | Unit4 - Avon Custom | Normal | Declining | Global | New_General Ledger | Application | Other | Enterprise | Richard.Hutchings | IT Global | Alex.Gooch | Finance | OS/400 | DB2/400 | RPG | IBM AS/400 | None | Replace | 1995-09-07 | 2014-12-31 |  | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous |  |  | 2012-09-21 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F8 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F9
Macpac | Macpac |  | Manufacturing and Purchasing | Manufacturing and Purchasing | Anderson Consulting - Avon Custom | High | Specialized | Local | Manage Supply Chain - Deliver | Application | Other | Other | Richard.Hutchings | IT ANZ | Richard.Jarvis | Supply Chain | OS/400 | DB2/400 | RPG | IBM AS/400 | None | Maintain | 1994-11-14 |  |  | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous | 48 to 60 hrs | 5 seconds to 24 hrs | 2012-09-21 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F8 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F9
RB3 | Representative Billing |  | Order and Representative Management System | Order and Representative Management System | Avon | Critical | Specialized | Local | Sell Products - Order Management | Application | Other | Other | Richard.Hutchings | IT ANZ | Richard.Jarvis | Supply Chain | OS/400 | DB2/400 | RPG | IBM AS/400 | None | Maintain | 1998-06-19 |  |  | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous | 48 to 60 hrs | 5 seconds to 24 hrs | 2012-09-21 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F8 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F9
SICS | SICS |  | Cartoning and IOPS | Cartoning and IOPS | Avon | Critical | Specialized | Local | New_order fulfillment | Active Directory | Service Oriented/Web | Other | Josh.Titley | IT ANZ | Michael.Anderson | Shipping | Windows | Oracle DB | C#/VB.NET/VB6 | HP x86 | None | Maintain | 1999-11-11 |  |  | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous | 12 to 24 hrs | 5 seconds to 24 hrs | 2012-09-21 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F8 | http://shareit.global.avon.com/sites/BKV2/it/default.aspx?RootFolder=/sites/BKV2/it/Procedure Documents/Disaster Recovery/Disaster Recovery Plan and Test Results 2012&FolderCTID=0x0120003F76D161694CE744B25EAEA00ED465F9
OLA | Online Appointments | 100% customized | Paperless appointments | Recruitment | Avon | Normal | Emerging | Local | Sell Products - Representative Support | Active Directory | Web Thin Client | Other | Richard.Hutchings | IT ANZ | Susanne.Groves | Sales | Windows | SQL Server | C# | HP x86 | Josh.Titley | Enhance | 2014-01-01 |  |  | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous | [5 empty] | No | No | Internal | Yes | Cold Site | Asynchronous
BlueFax | BlueFax | AS400 Module | BlueFax | AS/400 Email/Fax software |  | Normal |  | Local |  |  |  |  | Ulrich.Jensen | IT ANZ | [11 empty] | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous
Halcyon | Halcyon | AS400 Module | Halcyon | AS/400 SMS software |  | Critical |  | Local |  |  |  |  | Ulrich.Jensen | IT ANZ | [11 empty] | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous
Aldon | Aldon | AS400 Module | Aldon | AS/400 Source control/software deployment | Rocket Software | Normal |  | Local |  |  |  |  | Ulrich.Jensen | IT ANZ | [11 empty] | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous
Gumbo | Gumbo | AS400 tools for reporting | Gumbo | AS/400 report distribution software | Gumbo | Normal |  |  | Manage Corporate Services - Manage Information Technology |  |  |  | Ulrich.Jensen | IT ANZ | [11 empty] | No |  | No |  | Internal |  | Yes | Cold Site | Asynchronous