## CRs
Stage | # | CR | status | Next step | Who
Approved CR | 1 | Choice Product Feed Export | IT approval | Initial quotation | DSI
Approved CR | 2 | Google map usage tracking | IT approval | Initial quotation | DSI
Approved CR | 3 | Day to day process for ANZ (LPM update) | IT approval | Initial quotation | DSI
Approved CR | 4 | Representative store name URL | IT approval | Initial quotation | DSI
Approved CR | 5 | Representative Store Manager | pending business feedback | business feedback | cluster leaders
Approved CR | 6 | Opt-in Pop-up functionality | Business approval | Legal assesment | Mirek
Approved CR | 7 | Daily feed with order details | Business initial approval | IT approval (SOX) | Tara and Josh
Approved CR | 8 | Add FSC LN under product name | Business approval | IT approval | Alex
Approved CR | 9 | Repconsole orders tab UX | Moved to UX workstream | - | -
Approved CR | 10 | MIT Automated reset x-sellers | Business approval | IT approval | Alex
Approved CR | 11 | DCE Repconsole orders communication | Business approval | IT approval | Alex
Approved CR | 12 | MIT Automated Product Prioritisation | Business approval | IT approval | Alex
Approved CR | 13 | MIT Product Description field | Business approval | IT approval | Alex
Approved CR | 14 | Choice Engaging Error Pages | Business approval | IT approval | Alex
Approved CR | 15 | Rep Choice Auto Opt in | Requested | CR call approval | Mirek
Approved CR | 16 | Credit Card Transaction Reference Number | On Hold (directed by ANZ) |  | ANZ
Submitted & Pending Approval | ANZ017 | MIT: 'All four products’ Offer automation | Emailed to Mirek 25/09 | Response from Mirek | Mirek
Submitted & Pending Approval | ANZ018 | CUSTOMER PROFILING within Registration process | Emailed to Mirek 25/09 | Response from Mirek | Mirek
Submitted & Pending Approval | ANZ020 | DELIVERY OPTIONS HOVER ICONS ON THE DELIVERY TAB OF THE CART | Emailed to Mirek 25/09 | Response from Mirek | Mirek
Submitted & Pending Approval | ANZ024 | BACKGROUND IMAGE | Emailed to Mirek 25/09 | Response from Mirek | Mirek
Submitted & Pending Approval | ANZ025 | SALE COUNTDOWN ‘banner' | Emailed to Mirek 25/09 | Response from Mirek | Mirek
Business Case Development | ANZ004 | MIT REPORTING - High Priority | Simon / Adrian / David to discuss and build business case for submission | Submit to Mirek | Simon
Business Case Development | ANZ005 | PRODUCT AVAILABILITY - High Priority | Simon / Adrian to discuss | Submit to Mirek | Simon
Resubmitted & Pending Approval | ANZ008 | FIND A REPRESENTATIVE PAGE - Priority 1 v2.docx | Email sent to Mirek requesting a change | Response from Mirek | Mirek
Resubmitted & Pending Approval | ANZ010 | Product List Pages - Priority 1 | Emailed to Mirek 25/09 | Response from Mirek | Mirek
Resubmitted & Pending Approval | ANZ011 | Product List Pages 2 - Priority 1 | Email sent to Mirek with a question | Response from Mirek | Mirek

## ANZ Remedy Bugs
Incident ID*+ | Summary* | Status* | Priority* | Last Name+ | First Name+ | Company*+ | Reported Date+ | SLM Real Time Status | Incident Association Type | Assigned Group*+ | Assignee+ | Closed Date | Incident Type* | Last Modified By | Last Modified Date | Last_Kickback_Date | Responded Date+ | Submit Date | Target Date
INC000002747154 | Representative Who Is Demoted to -1 Causes 500 Error When Placing Direct Delivery Order | In Progress | High | TITLEY | JOSH | Avon - Australia | 4/29/2014 1:30:25 PM |  |  | DCE - DSI Support | NIALL COLLINS |  | Infrastructure Event | OSULLIVS | 6/18/2014 8:08:21 PM |  |  | 4/29/2014 1:43:52 PM
INC000002833114 | Omniture Is not picking up revenue and order information on the purchase confirmation page. | In Progress | High | GODWIN | SIMON | Avon - Australia | 6/19/2014 8:14:04 AM |  |  | DCE - DSI Support | NIALL COLLINS |  | User Service Request | OSULLIVS | 8/6/2014 11:02:15 PM |  | 6/19/2014 8:14:04 AM | 6/19/2014 8:19:45 AM
INC000002991940 | Missing ANZ DCE Orders | In Progress | High | GODWIN | SIMON | Avon - Australia | 9/18/2014 9:19:30 AM |  |  | DCE - DSI Support | MAURICE GLYNN |  | User Service Request | GLYNNM | 9/18/2014 7:15:59 PM |  |  | 9/18/2014 9:27:26 AM
INC000002968152 | MIT Load Error in C18 NZ | In Progress | High | GODWIN | SIMON | Avon - Australia | 9/4/2014 2:31:11 PM |  |  | DCE - DSI Support | SEAN O'SULLIVAN |  | User Service Request | GLYNNM | 9/5/2014 1:21:41 AM |  | 9/4/2014 2:31:11 PM | 9/4/2014 2:31:58 PM
INC000002975913 | QAF AU - Find a Representative page - Eligibility | In Progress | High | GODWIN | SIMON | Avon - Australia | 9/9/2014 2:48:07 PM |  |  | DCE - DSI Support | MAURICE GLYNN |  | User Service Request | GLYNNM | 9/9/2014 7:34:23 PM |  | 9/9/2014 2:48:07 PM | 9/9/2014 3:01:51 PM
INC000002975851 | QAF FAR Representative Ranking error | In Progress | High | GODWIN | SIMON | Avon - Australia | 9/9/2014 3:06:37 PM |  |  | DCE - DSI Support | MAURICE GLYNN |  | User Service Request | GLYNNM | 9/9/2014 7:30:34 PM |  | 9/9/2014 3:06:37 PM | 9/9/2014 3:26:01 PM
INC000002728040 | Voucher Display Isuse On Checkout | In Progress | Low | TITLEY | JOSH | Avon - Australia | 4/15/2014 10:32:53 PM |  |  | DCE - DSI Support | MAURICE GLYNN |  | Infrastructure Event | GLYNNM | 4/16/2014 1:56:44 AM |  |  | 4/15/2014 10:34:32 PM
INC000002751586 | Problem When Searching For Line Number Of Product Pulled | In Progress | Low | TITLEY | JOSH | Avon - Australia | 5/1/2014 12:14:56 PM |  |  | DCE - DSI Support | SEAN O'SULLIVAN |  | Infrastructure Event | OSULLIVS | 6/18/2014 8:43:17 PM |  |  | 5/1/2014 12:21:36 PM
INC000002751364 | Last Updated Field in MIT Updating When Nothing Has Changed | In Progress | Low | TITLEY | JOSH | Avon - Australia | 5/1/2014 8:34:09 AM |  |  | DCE - DSI Support | NIALL COLLINS |  | Infrastructure Event | OSULLIVS | 6/18/2014 8:29:31 PM |  |  | 5/1/2014 8:34:25 AM
INC000002725431 | Report an Incident | In Progress | Medium | GODWIN | SIMON | Avon - Australia | 4/14/2014 7:58:49 PM |  |  | DCE - DSI Support | MAURICE GLYNN |  | User Service Request | GLYNNM | 4/16/2014 1:48:30 AM |  |  | 4/14/2014 7:58:50 PM
INC000002728032 | Direct Delivery Cart Bugs To Be Cleaned Up | In Progress | Medium | TITLEY | JOSH | Avon - Australia | 4/15/2014 10:30:44 PM |  |  | DCE - DSI Support | MAURICE GLYNN |  | Infrastructure Event | TITLEYJ | 5/29/2014 5:18:25 PM |  | 4/15/2014 10:30:44 PM | 4/15/2014 10:32:22 PM
INC000002729642 | Report an Incident | In Progress | Medium | GODWIN | SIMON | Avon - Australia | 4/16/2014 4:44:35 PM |  |  | DCE - DSI Support | MAURICE GLYNN |  | User Service Request | GLYNNM | 4/17/2014 7:53:07 PM |  |  | 4/16/2014 4:44:36 PM
INC000002750257 | Unable To Edit Promotion | In Progress | Medium | TITLEY | JOSH | Avon - Australia | 4/30/2014 9:45:08 PM |  |  | DCE - DSI Support | NIALL COLLINS |  | Infrastructure Event | OSULLIVS | 6/18/2014 8:16:41 PM |  |  | 4/30/2014 9:47:20 PM
INC000002717802 | Able To Add Rep Only Products Bypassing Check | In Progress | Medium | TITLEY | JOSH | Avon - Australia | 4/9/2014 3:07:49 PM |  |  | DCE - DSI Support | MAURICE GLYNN |  | Infrastructure Event | TITLEYJ | 5/29/2014 5:26:38 PM |  |  | 4/9/2014 3:07:52 PM
INC000002768844 | Product With 2 Variants Shorting Is Completely Removed From Website | In Progress | Medium | TITLEY | JOSH | Avon - Australia | 5/13/2014 3:30:31 PM |  |  | DCE - DSI Support | SEAN O'SULLIVAN |  | Infrastructure Event | OSULLIVS | 6/18/2014 8:56:22 PM |  |  | 5/13/2014 3:30:34 PM
INC000002769035 | Product Not Pulled If All Variants Unavailable | In Progress | Medium | TITLEY | JOSH | Avon - Australia | 5/13/2014 3:37:09 PM |  |  | DCE - DSI Support | MAURICE GLYNN |  | Infrastructure Event | TITLEYJ | 5/29/2014 4:50:55 PM |  |  | 5/13/2014 3:37:55 PM
INC000002785348 | Unable To Publish C9 in QA | In Progress | Medium | TITLEY | JOSH | Avon - Australia | 5/22/2014 4:09:45 PM |  | Original | DCE - DSI Support | NIALL COLLINS |  | Infrastructure Event | OSULLIVS | 6/19/2014 12:22:15 AM |  |  | 5/22/2014 4:12:02 PM
INC000002797193 | The 'CONTACT ME >>' form under-developed | Pending | Medium | GODWIN | SIMON | Avon - Australia | 5/29/2014 1:22:18 PM |  |  | DCE - DSI Support | SEAN O'SULLIVAN |  | User Service Request | GLYNNM | 9/6/2014 12:42:29 AM |  | 5/29/2014 1:22:18 PM | 5/29/2014 1:29:28 PM
INC000002932477 | Incorrect reporting: Avon Online Customer Registration | In Progress | Medium | GODWIN | SIMON | Avon - Australia | 8/14/2014 11:57:01 AM |  |  | DCE - DSI Support | MAURICE GLYNN |  | User Service Request | GLYNNM | 8/14/2014 8:18:53 PM |  |  | 8/14/2014 11:57:02 AM
INC000002937083 | Sorting/Date issues with Customer Order History Sent to GI3 | In Progress | Medium | TITLEY | JOSH | Avon - Australia | 8/18/2014 11:02:59 AM |  |  | DCE - DSI Support | MAURICE GLYNN |  | User Service Request | GLYNNM | 8/28/2014 7:24:05 PM |  |  | 8/18/2014 11:04:03 AM
INC000002954421 | Report an Incident | In Progress | Medium | GODWIN | SIMON | Avon - Australia | 8/28/2014 12:02:36 AM |  |  | DCE - DSI Support | MAURICE GLYNN |  | User Service Request | GLYNNM | 8/28/2014 9:08:07 PM |  |  | 8/28/2014 12:02:37 AM
INC000002980503 | Double Transaction, One Order | In Progress | Medium | TITLEY | JOSH | Avon - Australia | 9/11/2014 2:13:20 PM |  |  | DCE - DSI Support | MAURICE GLYNN |  | Infrastructure Event | GLYNNM | 9/11/2014 7:59:38 PM |  |  | 9/11/2014 2:15:29 PM
INC000002963518 | NZ C18 all products are inactive | In Progress | Medium | GODWIN | SIMON | Avon - Australia | 9/2/2014 4:32:03 PM |  |  | DCE - DSI Support | SEAN O'SULLIVAN |  | User Service Restoration | GLYNNM | 9/2/2014 7:26:25 PM |  | 9/2/2014 4:32:03 PM | 9/2/2014 4:39:16 PM
INC000002963450 | Representative Delivery not offered despite the Representative contact checkbox being ticked. | In Progress | Medium | GODWIN | SIMON | Avon - Australia | 9/2/2014 4:41:22 PM |  |  | DCE - DSI Support | SEAN O'SULLIVAN |  | User Service Restoration | GLYNNM | 9/2/2014 7:23:56 PM |  | 9/2/2014 4:41:22 PM | 9/2/2014 4:45:39 PM
Sep 26, 2014 2:38 PM